## apk
BUG_ID | Date | Module | Bug Description/Quetions | Screenshot | status | Dev Comment | QA Comment
Done
1 | 2026-04-30 | Chatbot | The dataset contains the complete list of 99 Names of Allah. However, when the user asks for the full list, the chatbot returns only a partial response (~20 names) | https://prnt.sc/p7kre56BK5ED | Done
2 | 2026-04-30 | Chatbot | When the user selects “Dua Collection”, the chatbot displays a list of duas. However, the response is incomplete and gets truncated at item 7, showing only “7. D” instead of a full sentence. | https://prnt.sc/kGGYFcGldrwA | Done
3 | 2026-04-30 | Chatbot | The chatbot response for “Marriage Advice” is incomplete. The last point (point 5) is cut off and not fully visible ,Chatbot response gets truncated at last point | https://prnt.sc/ValBc_zYOddC | Done
4 | 2026-04-30 | Chatbot | Hadith response gets truncated / incomplete When requesting multiple hadiths, the chatbot response is partially cut off. The third hadith does not display completely, which affects readability and correctness of information. | https://prnt.sc/j6n6GGTmw_Xg | Done
5 | 2026-05-06 | Chatbot | When the user enters text in the search bar on the History screen, the list of history items does not get filtered. All items remain visible regardless of the search input. | https://prnt.sc/bcyZEOTmhuhQ | Done
6 | 2026-05-06 | Chatbot | When the user taps on the subscription button, no action is triggered. The button does not navigate to any screen, show any popup, or initiate any subscription flow. | https://prnt.sc/QJcePabUJtFk | Done
7 | 2026-05-06 | Chatbot | When the user taps on "Terms of Use" and "privacy policy" in Settings, the page opens but no content is displayed.(blank screen) |  | Done
8 | 2026-05-06 | Chatbot | Rate Us redirects to invalid Play Store link (Item not found).The Rate Us button redirects incorrectly or does not load the rating interface. | https://prnt.sc/krtrO7YpWtRz | Done
9 | 2026-05-06 | Chatbot | The Language option in Settings is not applying the selected language. | https://prnt.sc/GajjKt1Rx447 | Done
10 | 2026-05-06 | Chatbot | Back button does not navigate to previous screen on login screen |  | Done
11 | 2026-04-30 | Chatbot | Dream Interpretation does not align with Islamic perspective as mentioned in UI The Dream Interpretation feature states that it provides meanings from an Islamic perspective. However, the chatbot returns generic psychological interpretations without any Islamic context or reference. | https://prnt.sc/rHjAc6A3Z5iQ, | Done
12 | 2026-04-30 | Chatbot | When the user clicks on the Fatwa Assistant, the chatbot immediately displays a generic disclaimer message (“As an AI developed by OpenAI…”) without any user input. | https://prnt.sc/1NxqrqzNT_RK | Done
13 | 2026-04-30 | Chatbot | Upon clicking the Hadith Search feature, the chatbot responds that it does not have the functionality to search for hadiths. This contradicts the presence of the Hadith Search feature in the UI... | https://prnt.sc/bvmR2DTgl6xr,https://prnt.sc/QJcePabUJtFk | Done
14 | 2026-04-30 | Chatbot | When the user asks a topic-based question (e.g., “What is patience in Quran Explorer?”), the chatbot provides a generic explanation about patience instead of retrieving and displaying relevant Quran verses with proper references. When accessing the Hadith Search feature, the chatbot does not perform the expected search functionality. Instead, it responds with a generic message suggesting users consult external databases or scholars | https://prnt.sc/23-KDjyxfhnl,https://prnt.sc/edTHpRBgwBek | Done
15 | 2026-04-30 | Chatbot | Arabic Lessons module displays static text response instead of the promised step-by-step AI-guided Quranic Arabic learning experience with structured lessons and exercises. | https://prnt.sc/0898dvdsFSAe,https://prnt.sc/WcY_zoPaTzyS | Done
16 | 2026-04-30 | Chatbot | When opening the “Halal Food Guide” response in chat, the content is not fully displayed. The last point (Beverages) is cut off and ends abruptly (“All non-al…”), making the information incomplete and unclear. | https://prnt.sc/mnvmwNRz3cCC | Done
17 | 2026-05-06 | Chatbot | User is required to log in again every time after closing and reopening the app, even without logging out. |  | Done
18 | 2026-05-06 | Chatbot | Forgot Password Button Not Working On the Login screen, tapping the Forgot Password? text/button does not trigger any action | https://prnt.sc/lf77RI8gOv_- | Done
19 | 2026-05-06 | Chatbot | Sign Up / Complete Sign Up Button Not Working On the Sign Up screen, tapping the Complete Sign Up button does not perform any action. User is unable to proceed with account registration. | https://prnt.sc/UV5iV4r0Ff8G | Done
20 | 2026-05-06 | Chatbot | Input labels, placeholder text, and form fields on the Sign Up screen have very low contrast and are not clearly visible,on sign up screen | https://prnt.sc/UV5iV4r0Ff8G | Done
21 | 2026-05-06 | Chatbot | Social Login Boxes Not Working The two boxes/buttons displayed below or continue with section on the Sign Up screen are non-functional when tapped., on sign up screen |  | Done
|  | Chatbot |  |  | Done
22 | 2026-05-16 | Chatbot | Share functionality is not working properly. ,sharing content not fully display(see attachement) | https://drive.google.com/file/d/1QjsQlqFHG2qTJmlGpYKokddr2Gll1CZ0/view?usp=drive_link | Done
23 | 2026-05-16 | Chatbot | Questions Stuck on “Gathering Islamic Resources” Issue: When asking questions, app continuously shows “Gathering Islamic Resources” and responds take too much time | https://drive.google.com/file/d/1Qy-KdJ09VCMUQXgq_fM4tG7c5SwpRU33/view?usp=drive_link | Done
24 | 2026-05-16 | Chatbot | Voice Functionality Starts Automatically Issue: When a user asks a question, the chatbot voice response starts automatically. If the sound is muted during the response, the voice stops correctly. However, when the user turns the sound back on while the response is still ongoing, the voice does not resume automatically. | https://drive.google.com/file/d/1CtiRBV3bga4RRnWrP_wTPCLjE2eDuukB/view?usp=drive_link,https://drive.google.com/file/d/1dpNerqSJ2MtKzYmHBc3UtkWAphRzmiUa/view?usp=drive_link | Done
25 | 2026-05-16 | Chatbot | Copy option is not working for generated responses.(text is not copied in chat) | https://prnt.sc/FYGFb12wHR-7 | Done
26 | 2026-05-16 | Chatbot
27 | 2026-05-16 | Chatbot | Tapping history items does not open previous chats. | https://prnt.sc/ZCchjUQaEUbK | Done
28 | 2026-05-16 | Chatbot | Search functionality on history screen is not filtering results correctly.(some of them filtering but not all | https://drive.google.com/file/d/1fipMsLTOoV5RvPu_9jPgKeJ3MfVTzj-T/view?usp=drive_link | Done
29 | 2026-05-16 | Chatbot | Unable to Enter Card Details in Subscription Screen Issue: Input fields for card/payment details are not editable. | https://prnt.sc/WDGQ2Kz9kwWo,https://drive.google.com/file/d/17DFfj-_R9nk8DBC3JF-RSdTrhu8eG4VP/view?usp=drive_link | Done
30 | 2026-05-16 | Chatbot | History screen displays raw timestamp values with milliseconds. Example: 2026-05-16 13:29:18.981326 Expected Result: User-friendly format should display such as: 16 May 2026, 1:29 PM | https://prnt.sc/LaN-hARVZeAS,https://prnt.sc/pQYrRUuggqtq(in figma) | Done
31 | 2026-05-16 | Chatbot | Go Premium Button Not Working Issue: “Go Premium” button is unresponsive. | https://prnt.sc/2-SRYiH1i6jb | Done
32 | 2026-05-16 | Chatbot | Language Functionality Not Working Properly |  | Done
33 | 2026-05-16 | Chatbot | Payment history entries are not clickable/opening. | https://prnt.sc/oWFE26BIoCj3 | Done
34 | 2026-05-16 | Chatbot | Terms & Policy links/pages are not functioning correctly.(see in screenshot) | https://drive.google.com/file/d/1dpNerqSJ2MtKzYmHBc3UtkWAphRzmiUa/view?usp=drive_link | Done
35 | 2026-05-16 | Chatbot | Unable to login using email and password manually. | https://drive.google.com/file/d/1FPIrOX5F4_tE3tORBhj5bDgMoyLrx4HB/view?usp=drive_link | Done
36 | 2026-05-16 | Chatbot | Google login takes excessive loading time before showing email selection/login.(in login and sign up both screen) | https://drive.google.com/file/d/1Tqf3_S95rO1ui-k8E8Oef77C-ZMS8mq9/view?usp=drive_link,https://drive.google.com/file/d/1LdMdviR9TKOTBjsiUEjsCaEuXkvOslrR/view?usp=drive_link | Done
37 | 2026-05-16 | Chatbot | Back Button Not Working (log in,sign up,history,setting,chat almost all screens) |  | Done
38 | 2026-05-16 | Chatbot | back Button design is diffrent in some screens (see in attachmet) | https://prnt.sc/2-rJdTMUuOH8,https://prnt.sc/-23f_is3noDr | Done
39 | 2026-05-16 | Chatbot | “Continue with Apple” button is not working on Login screen ,sign up screen |  | Done
40 | 2026-05-16 | Chatbot | Clicking on “Try Another Email” does not navigate anywhere on Email Check screen. |  | Done
41 | 2026-05-16 | Chatbot | Clicking “Open Email App” redirects to google.com/mail in browser instead of opening installed email application directly. | https://drive.google.com/file/d/1Io7RQY7QIJolfYPt56NlUW3-JnmJbiot/view?usp=drive_link | Done
42 | 2026-05-16 | Chatbot | Subscription icon design does not match Figma. | https://prnt.sc/0bcXmUgjTkR-(in apk)(figma),https://prnt.sc/SIXbRbt1Hn0W | Done
43 | 2026-05-16 | Chatbot | Incorrect Year & Date Mismatch Issue: Payment history section headers show year as 2026, while transaction dates show 2025. | https://prnt.sc/4FszRl-ipnMx | Done
44 | 2026-05-16 | Chatbot | Chat Input Box UI Issue Issue: Chat input field appears disabled/faded and lacks proper active state visibility. | https://prnt.sc/QBtohUEHIzvd(in app),https://prnt.sc/o8jB6Gwn-1CH(in figma) | Done
45 | 2026-05-16 | Chatbot | AI Response Not Contextual Issue: App responds with generic prompt: “Please specify the Surah or topic…” instead of answering the asked query directly. | https://prnt.sc/uHrLjp3Y2qNb | Done
46 | 2026-05-16 | Chatbot | Evidence Gathering Loader Delay Issue: “Evidence Gathering” process takes excessive time before generating response. |  | Done
47 | 2026-05-16 | Chatbot | After requesting forgot password/reset password email, no reset link is received in email inbox.
48 | 2026-05-16 | Chatbot | Actual chatbot response design is different from the Figma design. Expected: Structured card-based response with: Highlighted sections Better spacing Evidence blocks Styled Quran/Hadith containers Compact readable UI Actual: Response appears as long plain text paragraphs with poor visual hierarchy | https://prnt.sc/8cHmzRCSAYFn,https://prnt.sc/oLKl0V9-C3mB(in apk),https://prnt.sc/BvmTlbnT_tAR(in figma) | Done
49 | 2026-05-16 | Chatbot | The evidence rows should display proper blue tick/check indicators before verified evidence messages exactly as designed in the Figma reference UI. | https://prnt.sc/PE0ueL3dhYnl(in apk),https://prnt.sc/hQca69rR49m9(in figma) | Done | Need image asap
50 | 2026-05-16 | Chatbot | Chatbot returns unrelated Hadith results when the user only requests a Quran Surah. The response should focus only on the requested Surah unless additional references are explicitly requested.” | https://prnt.sc/BBv6BWYIELCj | Done
51 | 2026-05-16 | Chatbot | When the user enters “Quran Explorer”, the chatbot responds with: “Please specify the Surah or topic you would like to explore in the Quran…” This indicates the chatbot is not understanding the feature intent properly. Instead of opening or showing Quran exploration content/categories, it asks for another input. | https://prnt.sc/aM35DGhjyHQn | Done
52 | 2026-05-16 | Chatbot | splash screen of chatbot does not propely structured UI (images should be in centered) | https://prnt.sc/CtkDGkX7p7Ln,https://prnt.sc/AOAXygkPLJED, | Done
53
54 | 2026-05-22 | Chatbot | When user searches the same query multiple times (e.g., "Islamic History"), the History section creates duplicate entries for the same query. Also, the previously searched response gets replaced/removed and only the latest searched response is shown. | https://drive.google.com/file/d/1PM_R_bCNl58s9ptMPKR-NjpbdFBLFCWu/view?usp=drive_link | Done
55 | 2026-05-22 | Chatbot | back botton is not working on some screens |  | Done
56 | 2026-05-22 | Chatbot | Text gets copied successfully but no confirmation or visual feedback is shown to the user. |  | Done
57 | 2026-05-22 | Chatbot | Card number field not accepting input properly Expiry/CVV fields not responding Country dropdown not functioning correctly Pay button not working/responding Payment process does not continue after entering details | https://prnt.sc/LgauNQTijSAI(in apk),https://prnt.sc/enKFAnYOgCcR(in figma) | Done
58 | 2026-05-22 | Chatbot | On the Subscription screen, payment-related elements/buttons are visible but not functioning when interacted with. | https://prnt.sc/SDIbd2snE-4a | Done
59 | 2026-05-22 | Chatbot | need confirmation regarding the “Go Premium” button functionality on the subscription screen. Since monthly and yearly premium plans are already visible, should the “Go Premium” button perform any additional action (navigation/highlight/payment flow), or is it only for UI display? | https://prnt.sc/9FUQactk8Lqq | Done
60 | 2026-05-22 | Chatbot | There is UI diffrence in subscription box (monthly and yealry plans) from figma | https://prnt.sc/s6jzP6J1Ilb8(in figma),https://prnt.sc/H9TMPb0c0QLa,https://prnt.sc/4IdSrlyRh4WI(in apk) | Done
61 | 2026-05-22 | Chatbot | there are some UI differences between the APK and Figma design, such as card spacing, padding, and alignment. | https://prnt.sc/krMSQW-_2u8O(in figma),https://prnt.sc/gDCzr4bcrroc(light mode),https://prnt.sc/pGhXKDtoFnoB(dark mode) | Done
62 | 2026-05-22 | Chatbot | need confirmation regarding payment history section "the section headings show 2026 while the transaction dates inside the cards show 2025. I noticed the same behavior is also present in the Figma design. Could you please confirm whether this is intentional or should both years match?" | https://prnt.sc/U-v1KCCDHM7A | Done
63 | 2026-05-22 | Chatbot | Need confirmation regarding the Payment History items — when a user taps on any transaction card, should it open any detailed screen, invoice, or transaction information? Currently, no action is happening on click. | https://prnt.sc/U-v1KCCDHM7A
64 | 2026-05-22 | Chatbot | "share with friends" functionality not working propely see in attachment | https://drive.google.com/file/d/1jWIcwMqNn1I7ghnbE8mX3iUMTPTsjUF9/view?usp=drive_link | Done
65 | 2026-05-22 | Chatbot | "Rate us " functinality is not working
66 | 2026-05-22 | Chatbot | APK: Response container looks slightly off-centered and stretched. Left and right spacing are not balanced like Figma. Message box occupies more width. | https://prnt.sc/SYN7_MVbmw37(in figma),https://prnt.sc/9gb0DyeTYOlR(in apk) | Done
67 | 2026-05-22 | Chatbot | Search box in History screen is not matching the Figma design. In APK, the search placeholder text and icon visibility are low/faded compared to the Figma design, | https://prnt.sc/KxcJ0czydmf0(in apk),https://prnt.sc/tOWFEw9ccwjp(in figma) | Done
68 | 2026-05-22 | Chatbot | After searching “Halal Food Guide”, the history card is showing the tag “General” instead of a relevant category related to Halal Food. The displayed category/tag does not properly match the searched content. | https://prnt.sc/J87we9jF8MBS(in figma),https://prnt.sc/E-2DyUhiz-P9(in apk) | Done
69 | 2026-05-22 | Chatbot | There are only 4 onboarding spalsh screen visible in app and in figma there six(Need confirmation) | https://drive.google.com/file/d/15RE_Ez1bSm5iGCQUXb6KnT479GHFd-rr/view?usp=drive_link(in apk),https://prnt.sc/SoGy0lQRfyDo(in figma) | Done
70 | 2026-05-22 | Chatbot | after updating password these two scrren as visible in figma not visible in apk see in attachemnt | https://prnt.sc/SO9gF05-O3Er(in figma),https://drive.google.com/file/d/1R5pff59qjQOcHCCqWteEHlvVlM853WE5/view?usp=drive_link(in apk)
71 | 2026-05-22 | Chatbot | Some questionss response format are diffrent from others responses and figma design see in attachment | https://prnt.sc/bairyIcpex4K,https://prnt.sc/Bg-uJpWPVRAz,https://prnt.sc/b5IZH1mj_yPS,https://drive.google.com/file/d/1_JjjmuHOIVrdHxa6-zVxoIvt2CQEaNrz/view?usp=drive_link | Done
72
73 | 2026-05-26 | Chatbot | After changing app language to Hindi, chatbot responses are appearing in mixed languages including Hindi, English, and Arabic instead of proper Hindi responses. |  | Done
74 | 2026-05-26 | Chatbot | History items are showing inconsistent category tags. Some topics display specific tags like “Quran” and “Prayer”, while other topic-specific searches are incorrectly displayed under the generic “General” tag. | https://prnt.sc/MKGyP-Ma19Gn,https://prnt.sc/REHKP0fNR_sm | Done
75 | 2026-05-26 | Chatbot | In the History screen search, some history items are filtered correctly while others do not appear even when relevant keywords are searched. | https://drive.google.com/file/d/1e-Iw0hb0g7bDAhl0t6dDtkVd7Yciygeh/view?usp=drive_link | Done
76 | 2026-05-26 | Chatbot | The chatbot response card/container alignment in the APK does not match the Figma design. In the design, the response section is properly centered, whereas in the APK it appears slightly left-shifted. | https://prnt.sc/UyBe3C1qYTc7(in figma) , https://prnt.sc/UUm6vGm59djv(in apk) | Done
77 | 2026-05-26 | Chatbot | Previously, chatbot responses were loading within approximately 25–30 seconds, but now response times are inconsistent and sometimes take 35–60 seconds. | https://drive.google.com/file/d/1wSFOHtfRhugVKmiv6gbF4FbLTbOwXe1-/view?usp=drive_link
78 | 2026-05-26 | Chatbot | After changing the app language to Hindi, the chatbot response content appears in Hindi, but the “Evidence Gathering” section and its labels are still displayed in English. | https://prnt.sc/-K6GwXwpUppL , https://prnt.sc/42KmxZM6qIGc
79 | 2026-05-26 | Chatbot | In the Forgot Password flow, clicking the reset link opens both Chrome browser and the Islamic Chatbot APK. The reset flow works properly in Chrome, but when opened in the APK it shows a blank screen. | https://drive.google.com/file/d/1jdESPQzrvxAMeFgFT6_3WbC_olipXSHA/view?usp=drive_link
80 | 2026-05-26 | Chatbot | "Google sign in failed in apk" is failed not login in successfully | https://drive.google.com/file/d/1891tkMV5cni4aRKlN4o8UgJZkxrwCawH/view?usp=drive_link | Done
81 | 2026-05-26 | Chatbot | history page should be back on history rather than home page of apk | https://drive.google.com/file/d/12-TUd6Fl2Zdp8pd5B-KQTR4sxg29Fy6J/view?usp=drive_link | Done
82
83 | 2026-05-28 | Chatbot | Chat screen auto-scroll issue: When user sends a new message while scrolling on old/top chats, screen does not automatically navigate to the latest question/response. User has to manually scroll down to see the new response. | WhatsApp Video 2026-05-27 at 21.40.04.mp4 | Done
84 | 2026-05-28 | Chatbot | The Islamic AI chatbot is showing inconsistent behavior when handling unrelated, invalid, and edge-case user queries. Some non-Islamic questions are restricted correctly, while others receive general knowledge responses. Chatbot sometimes restricts non-Islamic questions with messages like: “I’m here to provide Islamic knowledge...” However, some unrelated queries still receive full general knowledge answers. Example: “can cats fly?” → chatbot gives scientific/general answer instead of restricting the query. | WhatsApp Video 2026-05-27 at 21.38.04.mp4
85 | 2026-05-28 | Chatbot | The shared response appears partially truncated, text structure is dense, query/response sections are not clearly separated, and the generated link redirects only to the app/play store instead of opening the complete shared conversation. | https://prnt.sc/4e27V1CLzZpp | Done
86 | 2026-05-28 | Chatbot | When searching for “99 Names of Allah”, multiple names are repeated in the response with different numbering. Due to duplicate entries, the list does not appear to contain 99 unique names. The response initially displays numbered circular badges, but later switches to plain text numbering format, causing inconsistent UI presentation. Because of repeated names, the numbering/order of the 99 Names appears incorrect and confusing. | WhatsApp Video 2026-05-27 at 21.38.51.mp4 | Done
87 | 2026-05-28 | Chatbot | Chatbot response formatting looks cluttered on mobile UI. Response is in excessive spacing, divider lines, and dense text blocks..... | WhatsApp Video 2026-05-27 at 21.38.51.mp4 | Done
88 | 2026-05-28 | Chatbot | Chatbot is not properly handling follow-up conversation context. After asking an initial question about “Prophet Ibrahim,” the chatbot fails to understand pronouns like “his” and “him” in subsequent follow-up queries. Instead of continuing the same conversation context, the chatbot either asks for unnecessary clarification or generates unrelated responses. During testing: Query: “Who was Prophet Ibrahim?” Follow-up: “who was his son” Further follow-up: “tell more about him” The chatbot failed to identify that “his/him” referred to Prophet Ibrahim and later generated an unrelated response about “Allah.” This indicates an issue with conversation memory retention, pronoun resolution, and contextual understanding in follow-up interactions. 2. When user asks a follow-up query like “can u please explain me it in short”, the chatbot does not summarize the previous response. Instead, it generates an unrelated/new topic response (“What is Tahajjud?”), causing context mismatch. | WhatsApp Video 2026-05-27 at 21.03.55.mp4, WhatsApp Video 2026-05-29 at 19.43.51.mp4 | Done
89 | 2026-05-28 | Chatbot | Chatbot response time is inconsistent for different user queries. Some responses generate in 15 seconds. Some take 30–40 seconds. Some queries take around 1 to 1.5 minutes. |  | Done
90 | 2026-05-28 | Chatbot | query Asked: “can muslim eat pork” Issues Observed: Wrong Hadith shown in response. The chatbot displayed a Hadith related to alcohol instead of pork consumption. Source mismatch issue. Top evidence section shows “Sahih Ibn Majah” but detailed response shows “Sahih Muslim 1982”. Response is too lengthy for a simple question. User asked a direct question, but chatbot generated a very long explanation. UI formatting can be improved. Response contains too many separators and long paragraphs | WhatsApp Image 2026-05-29 at 09.28.43 (1).jpeg,WhatsApp Image 2026-05-29 at 09.28.43.jpeg
91 | 2026-05-28 | Chatbot | History items are showing inconsistent category tags. Some topics display specific tags like “Quran” and “Prayer”, while other topic-specific searches are incorrectly displayed under the generic “General” tag. | https://prnt.sc/MKGyP-Ma19Gn,https://prnt.sc/REHKP0fNR_sm | Done
92 | 2026-05-28 | Chatbot | In the History screen search, some history items are filtered correctly while others do not appear even when relevant keywords are searched. | Record_2026-05-25-16-18-19_5ef0906528d611e89e321312acceeef3.mp4 | Done
93 | 2026-05-28 | Chatbot | For some chatbot responses, the “response gathering” box is displayed, while for some responses it is not visible. |  | Done
94 |  | Chatbot |  |  | Done
95 | 2026-06-06 | Chatbot | when users tap feature tabs such as Fatwa Assistant, Qibla Direction, Islamic History, and other similar modules, the chatbot immediately returns a detailed informational answer. As per the expected user flow, these feature tabs should ideally provide a brief introduction or welcome message related to that feature (e.g., "Hi, I'm here to assist you with Fatwa-related questions" or "I can help you find the Qibla direction"), allowing the user to then ask a specific question. Currently, the chatbot directly generates detailed content instead of introducing the selected feature | https://drive.google.com/file/d/1P3blKNqN3581GmOnPuxnvJ8Aq8emvzkE/view?usp=sharing | Done
96 | 2026-06-06 | Chatbot | After starting a new chat, the chatbot is still using context from previous conversations. For example, follow-up questions like "Give me more details" or "When does it happen?" are being answered based on topics discussed in an earlier chat instead of asking for clarification. The chatbot also remembers previously shared information (e.g., favorite color) across chats. Each new chat should start with a fresh context and maintain separate chat history. | WhatsApp Video 2026-06-06 at 21.18.34.mp4, WhatsApp Video 2026-06-06 at 21.22.05.mp4 | Done
97 | 2026-06-06 | Chatbot | the chatbot returns the same generic capability response for "What can you do for me?" across different conversation contexts. For example, after asking about Fatwa Assistant and then asking "What can you do for me?", the bot provides a capability response. In a separate new chat, after asking about Qibla Direction and then asking the same question, the bot returns the same response again. As per the requirement, capability-related queries should be context-aware and adapt based on the current topic or feature being discussed, rather than always returning the same generic response. | https://drive.google.com/file/d/1wW2_QfmrJd6lvk4Z0hptFRl7_dY2xIul/view?usp=sharing | Done
98 | 2026-06-20 | Chatbot
99 | 2026-06-20 | Chatbot | What are the similarities and differences between Surah Al-Fatiha and Surah Al-Ikhlas? | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
100 | 2026-06-20 | Chatbot | What is the relationship between patience, gratitude, and faith according to the Quran? | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
101 | 2026-06-20 | Chatbot | Find the narrations that demonstrate the Prophet’s method of communication with different groups of people. | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Not fixed
102 | 2026-06-20 | Chatbot | Analyze the relationship between Hadith collections and Fiqh-oriented books in the dataset, and explain how scholars used Hadith literature to derive legal rulings. | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
103 | 2026-06-20 | Chatbot | What is the difference between Ar-Rahman and Ar-Raheem | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
104 | 2026-06-20 | Chatbot | What common theme exists between As-Salam and Al-Mu'min? | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
105 | 2026-06-20 | Chatbot | What names of Allah would be most relevant for someone facing hardship and seeking comfort? | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
106 | 2026-06-20 | Chatbot | Dream interpretations tab question -> What is the difference between a true dream and a nightmare in Islam? | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Not fixed
107 | 2026-06-20 | Chatbot
108 | 2026-06-20 | Chatbot | quetions from "Prayer Times" -> what is prayer times for fajr | https://gyazo.com/8d43edf0a21726117638595220466066,https://gyazo.com/2ee6a8b0ea6f9fb419e2293a138fe362,https://gyazo.com/8c69f1680734072f481aaf98fc7ae254 | Done
109 | 2026-06-20 | Chatbot | Quetions from "Quibla direction" -> where is the qibla direction from my location | WhatsApp Video 2026-06-22 at 09.17.38 (2).mp4 | Done
110 | 2026-06-20 | Chatbot | show me the qibla direction | WhatsApp Video 2026-06-22 at 09.17.38.mp4 | Done
111 | 2026-06-20 | Chatbot | When users ask different Islamic questions and then request a short explanation (e.g., "Explain in short", "Can you explain this briefly?"), the chatbot returns the same generic response about the Dua of Prophet Yunus regardless of the original question. The response is not contextually related to the user's query. | WhatsApp Video 2026-06-20 at 15.03.22.mp4 | Not fixed
112 | 2026-06-20 | Chatbot | islamic life -> halal food guide quetions - > what are differences between halal and haram | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
113 | 2026-06-20 | Chatbot | what are differences between halal and haram food | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
114 | 2026-06-20 | Chatbot
115 | 2026-06-20 | Chatbot | Compare Al-Umm with Ikhtilaf al-Hadith in terms of purpose, methodology, and contribution to Islamic jurisprudence. | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
116 | 2026-06-20 | Chatbot | what differences can be found between the translation "Adam" ,"o Adam", and "to Adam" | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
117 | 2026-06-20 | Chatbot | What similarities and differences can be identified between Al-Quddus and As-Salam regarding perfection and freedom from imperfection? | https://gyazo.com/08167f34212a76fc6b8424cd89ff5247 | Done
118
119 | 2026-06-22 | Chatbot | When asked "Which party should I vote for?", the chatbot provides political decision-making guidance and voting recommendations instead of declining political advice or redirecting the user to neutral information.("which party should i vote for") | WhatsApp Video 2026-06-22 at 09.41.30.mp4 | Done
120 | 2026-06-22 | Chatbot | "which political party should i vote for" | WhatsApp Video 2026-06-22 at 09.41.30 (1).mp4 | Done
121 | 2026-06-22 | Chatbot | The chatbot fails to maintain conversation context and returns an unrelated explanation of Quran 6:65 when asked to briefly explain its previous voting-related response. | WhatsApp Video 2026-06-22 at 09.41.39.mp4 | Done
122 | 2026-06-22 | Chatbot | User entered a personal statement ("My favourite fruit is mango"), but the chatbot returned an unrelated response instead of recognizing the input as a non-Islamic statement. | WhatsApp Video 2026-06-22 at 10.09.52.mp4 | Not fixed
123 | 2026-06-22 | Chatbot | The chatbot responds to a political query and provides political guidance instead of declining or restricting the response to Islamic knowledge content.(critize a political party and more query like as...) | WhatsApp Video 2026-06-22 at 10.24.58.mp4 | Done
124 | 2026-06-22 | Chatbot | The chatbot does not handle negative/out-of-scope queries correctly. Instead of politely declining or redirecting the user to Islamic topics, it generates responses for political, insulting, harassment, or other non-Islamic queries. | WhatsApp Video 2026-06-22 at 10.26.29.mp4 | Done
125 | 2026-06-23 | Chatbot | For a mixed-type query containing both Islamic and non-Islamic topics, the chatbot answered both parts. Please confirm if this behavior is intended.** | WhatsApp Video 2026-06-22 at 12.00.16.mp4 | Not fixed
126 | 2026-06-23 | Chatbot | The chatbot fails to maintain conversation context in follow-up queries. When asked "Tell me more about it," it generates information about an unrelated topic (Hā Mīm) instead of continuing the previous discussion. | WhatsApp Video 2026-06-22 at 12.00.16.mp4 | Not fixed
127 | 2026-06-23 | Chatbot | For a mixed-type query containing both Islamic and non-Islamic topics, the chatbot declined the entire query instead of answering the Islamic part ("What is Islam"). Please confirm whether the chatbot should answer the in-scope portion of mixed queries or reject the entire query. | WhatsApp Video 2026-06-22 at 12.03.28.mp4 | Done
128 | 2026-06-23 | Chatbot | The response explains dreams in Islam generally but does not directly answer the user's requested comparison between true dreams and nightmares, resulting in an intent mismatch. | WhatsApp Video 2026-06-23 at 11.13.45.mp4
129 | 2026-06-23 | Chatbot | The chatbot failed to maintain conversational context. After correctly explaining Hadith, the follow-up request 'Can you explain it in short?' should have generated a concise summary of the previous answer. Instead, the chatbot provided an unrelated response about Quran 5:82 and Christians, | WhatsApp Video 2026-06-23 at 11.18.11.mp4 | Not fixed
130 | 2026-06-23 | Chatbot | For the question "Which questions I asked you above?", the chatbot failed to recall previous conversation context and returned a generic greeting instead of listing the user's earlier questions. | WhatsApp Video 2026-06-23 at 11.25.54.mp4 | Not fixed
131 | 2026-06-23 | Chatbot | Chatbot returned an irrelevant response unrelated to the user's query. Instead of acknowledging or processing the city information ("Jaipur"), it generated an incorrect Umrah-related answer, | WhatsApp Video 2026-06-23 at 11.40.24.mp4 | Not fixed
132 | 2026-06-23 | Chatbot | The chatbot ignored the user's request and returned an unrelated answer about writing the name of Allah on the body for healing, including explanations, Quranic references, and scholarly opinions instead of providing 10 names of Allah. | WhatsApp Video 2026-06-23 at 11.46.41.mp4 | Done
133 | 2026-06-23 | Chatbot | Chatbot shows inconsistent behavior for identical repeated queries. The first request returns the correct list of 10 names of Allah, but subsequent requests generate unrelated content, indicating context drift | WhatsApp Video 2026-06-23 at 11.46.51.mp4 | Done
134 | 2026-06-23 | Chatbot | Mixed query handling issue – chatbot ignores the valid Islamic question when a non-Islamic request is included. | WhatsApp Video 2026-06-23 at 11.56.59.mp4
135 | 2026-06-23 | Chatbot | Context retention issue – chatbot fails to associate "it" with Islam and responds with an unrelated topic. | WhatsApp Video 2026-06-23 at 11.56.59.mp4 | Not fixed
136 | 2026-06-23 | Chatbot | Conversation Summarization Failure – When asked to combine previous points, the chatbot generates unrelated content not present in the conversation history. | WhatsApp Video 2026-06-23 at 12.01.25.mp4g | Not fixed
137 | 2026-06-23 | Chatbot | Chatbot incorrectly rejects the question "Compare prayer practice in Islam and how does that differ from Christianity?" despite it being a valid Islam-related comparative inquiry. Instead of providing relevant information, the chatbot returns a generic refusal and fails to answer the user's question. | Assalamu Alaikum wa Rahmatullahi wa Barakatuh! Thank you for your question. I can only answer Islamic questions. Please ask something related to Islam.
138 | 2026-06-23 | Chatbot | When asked, "Should I leave Islam and follow another religion?", the chatbot responded from an exclusively Islamic perspective and primarily encouraged the user to remain within Islam. The response lacked a balanced, neutral approach and did not adequately support independent exploration of the user's question | WhatsApp Video 2026-06-23 at 12.10.29.mp4
139 | 2026-06-23 | Chatbot | The chatbot failed to classify the book titles from the provided dataset and instead analyzed individual hadith documents. It incorrectly categorized all entries as Hadith-based content and did not perform the requested title-level classification into Hadith, Tafsir, Fiqh, Zuhd, or Islamic Governance categories. | WhatsApp Video 2026-06-23 at 12.16.46.mp4
140 | 2026-06-23 | Chatbot | Title: Islamic chatbot incorrectly rejects valid Islamic question about Muwatta Malik narrations. Question Asked: "Compare the different narrations of Muwatta Malik mentioned in the dataset and explain how the narrators may affect the transmission and scholarly value of the text." | Assalamu Alaikum wa Rahmatullahi wa Barakatuh! Thank you for your question. However, I can only answer Islamic questions. Please ask something related to Islam.
141 | 2026-06-23 | Chatbot | Question Asked: "Which verses focus on guidance?" Actual Response Received: The chatbot provided a lengthy explanation about guidance in Islam, cited Surah Al-Baqarah 2:2, included a hadith reference, and discussed general concepts of guidance, piety, mercy, and Ramadan. However, it did not directly list the Quranic verses that focus on guidance. | WhatsApp Video 2026-06-23 at 12.24.02.mp4
142 | 2026-06-23 | Chatbot | Dream interpretesion - > quetion -> Why does Islam distinguish between true dreams, nightmares, and thoughts from the subconscious? | I can only assist with authentic Islamic questions based on the Quran and Hadith. Please ask an Islamic question.
143 | 2026-06-23 | Chatbot | Question Asked: User: "all prayers time's for today" Chatbot: "Please share your location or city." User: "Jaipur" Actual Response: The chatbot provided information about Umrah, Ihram, and Meeqaat instead of prayer times. | WhatsApp Video 2026-06-23 at 12.34.52.mp4 | Done
144 | 2026-06-23 | Chatbot | Initial Question: "tell me all duas name in islam and short one line description" Follow-up Question: "can u explain number 1 dua in short" (Number 1 in the previous list was Dua for Guidance (Istikhara).) Actual Response: The chatbot gave a lengthy explanation about the general importance of dua, sincerity, persistence, humility, and included Quran and Hadith references. It did not explain Istikhara specifically. | WhatsApp Video 2026-06-23 at 12.39.17.mp4
145
146 | 2026-06-25 | Splash screen | Expected (Figma): "Ask Islam Anything" text appears dark navy/black. Actual (APK): Heading appears lighter grayish-black, making it less prominent. (do this same for all six splach screens) | https://gyazo.com/94b6e589aeb9a02c999ea8678089c99c,https://gyazo.com/0d33af3c3d179b1f3aa7abb0cb427524
147 | 2026-06-25 | Splash screen | Skip button background color differs from the Figma design (do this same for all six splach screens) | https://gyazo.com/94b6e589aeb9a02c999ea8678089c99c
148 | 2026-06-25 | Splash screen | Get started button color does not match Figma.(do this same for all six splach screens) | https://gyazo.com/94b6e589aeb9a02c999ea8678089c99c
149 | 2026-06-25 | login screen | Heading font weight/style does not match Figma (APK text is thinner/lighter). Forgot Password text alignment/position differs from Figma. | https://gyazo.com/a88055b6ef98fe82e09f03d9230f2b68,https://gyazo.com/8fd37d19718fa045bab428d05fc96179
150 | 2026-06-25 | login screen | Email input field border color/style does not match Figma. Email placeholder text is different from the design. | https://gyazo.com/a88055b6ef98fe82e09f03d9230f2b6
151 | 2026-06-25 | login screen | Login button gradient colors differ from Figma. "Don't have an account? Let's Create" text spacing and styling are different. | https://gyazo.com/a88055b6ef98fe82e09f03d9230f2b6
152 | 2026-06-25 | Home screen (for all tabs) | Search box background color mismatch – Search box is more highlighted/darker gray in Figma, but appears lighter in APK. . | https://gyazo.com/e91523a16569752662dedd70ae3cab5f,https://gyazo.com/eebbe33fdb85b6f3290d5c4ee8ac0a04
153 | 2026-06-25 | Home screen (for all tabs) | Tab text font weight mismatch – "Quran & Hadith", "Prayer", "Islamic Life", and "Learn" tab labels are bolder in Figma but appear lighter in APK. | https://gyazo.com/e91523a16569752662dedd70ae3cab5
154 | 2026-06-25 | Home screen (for all tabs) | Card title font weight mismatch – Card headings such as "Quran Explorer", "Hadith Search", "99 Names of Allah", and "Dream Interpretation" are bolder in Figma but lighter in APK | https://gyazo.com/e91523a16569752662dedd70ae3cab5
155 | 2026-06-25 | History | Card height is larger in APK – APK cards have too much vertical spacing, while Figma cards are more compact. | https://gyazo.com/98a4b3b8f3df1cdbba5a0d61a866b602,https://gyazo.com/bc45596f2691c846cbe618e7c8e5e694
156 | 2026-06-25 | History | Title font size is larger in APK – Text like "99 Names of Allah" appears bigger than in Figma. | https://gyazo.com/98a4b3b8f3df1cdbba5a0d61a866b60
157 | 2026-06-25 | History | Date format is different Figma: 7/4/26 APK: 25/06/2026
158 | 2026-06-25 | History | Date format is different Figma: 7/4/26 APK: 25/06/2026 | https://gyazo.com/98a4b3b8f3df1cdbba5a0d61a866b602
159 | 2026-06-25 | History | Description area mismatch – Figma shows longer question text with proper wrapping, while APK shows a short greeting text and leaves a lot of empty space. | https://gyazo.com/98a4b3b8f3df1cdbba5a0d61a866b602
160 | 2026-06-25 | Settings | Bottom branding ("IslamGPT") position mismatch – APK branding is placed slightly lower. "powered By" text style mismatch | https://gyazo.com/056f0401a0b55c5ce577b101b26d50d4,https://gyazo.com/d69add5b1937493b5da9ae929da44d65
161
162
163 | 2026-06-25 | Settings | toggle button design mismatch APK toggle is larger than Figma | https://gyazo.com/d69add5b1937493b5da9ae929da44d65
164 | 2026-06-25 | Settings | "SETTINGS" heading style mismatch Figma: Uppercase ("SETTINGS") APK: Sentence case ("Settings") APK text is lighter and smaller. | https://gyazo.com/056f0401a0b55c5ce577b101b26d50d4
165 | 2026-06-25 | Settings | And all text visible in figma are bolder and in apk little light | https://gyazo.com/056f0401a0b55c5ce577b101b26d50d4
166 | 2026-06-25 | Subscription | On subscriptions page there is /mo visible after $25 | https://gyazo.com/7e0641cf991788d2e4ed9669d9de51f6,https://gyazo.com/dd7607ca0d315cb3fc08a311d4332458
167 | 2026-06-25 | Subscription | Add card, united states,save card for faster payments text are bolder in figma and others are gray light | https://gyazo.com/7e0641cf991788d2e4ed9669d9de51f6,https://gyazo.com/86751346992af7662f02536acee4752e
168 | 2026-06-25 | Payment history | On payment history back icon is different from figma | https://gyazo.com/28b21dc0e2c330f97b76aa3af498b49e,
169 | 2026-06-25 | Payment history | Text style is diffrent from figma | https://gyazo.com/28b21dc0e2c330f97b76aa3af498b49e
170 | 2026-06-25
171 | 2026-06-25 | Sign up | On sign up page Calender structure is diffrent freom figma design | https://gyazo.com/674f082dabc00e6602c195162675f86d,https://gyazo.com/fac9db2ad8424648ff6397e725612184
172 | 2026-06-25 | Sign up | On sign up page All field is bolder in figma and light in apk
173 | 2026-06-26 | Chat screen | : The feedback popup is always displayed in English, even after changing the app language. | WhatsApp Video 2026-06-26 at 10.56.09.mp4
174 | 2026-06-26 | Chat screen | chat sharing icon and copy icon is diffrent design in apk mismatch with figma (APK: The copy icon is inside a large light gray circular button.0) | https://gyazo.com/30b4340647f75d16c3135d775995515f,https://gyazo.com/9d1e6abb2330513923ce722b3f00afae
175 | 2026-06-26 | Chat screen | Message timestamp position is incorrect. In Figma, the timestamp is left-aligned, but in the app it is right-aligned. | https://gyazo.com/f2d3b924641f794cc18db4125a41305d
176 | 2026-06-26 | subscription | on "or pay using" text there is a line on figma design but in ap line is not visible | https://gyazo.com/b2c8f12f22aad4cb9173b8280e70be79
177 | 2026-06-26 | CHat screen | Old messages are showing today's current time instead of the original timestamp. | Record_2026-06-26-11-35-26_67e6e985d405a1fef171e1c945683053.mp4
178
179 | 2026-06-27 | Admin panel(login and forget passwordscreen) | Logo mismatch – The logo/icon used in the admin panel is different from the Figma design. | https://gyazo.com/edad5393ec2fe0a9d2c59035ece59124,https://gyazo.com/41e9c36849f02f55cdc436b00f151380,https://gyazo.com/dfabbabce5535d4bdcc6659bd8240f2a |  | designer told me logo is not finalized.
180 | 2026-06-27 | Admin panel(login screen) | "ADMIN PORTAL" Text styling mismatch – The badge in the admin panel is larger and has different padding compared to the Figma design. | https://gyazo.com/edad5393ec2fe0a9d2c59035ece5912,https://gyazo.com/dfabbabce5535d4bdcc6659bd8240f2a | done
181 | 2026-06-27 | Admin panel(login screen) | "Email Adderess" and "password " text should be bold like figma | https://gyazo.com/edad5393ec2fe0a9d2c59035ece5912 | done
182 | 2026-06-27 | Admin panel(login screen) | Login button text and icon mismatch -> Figma shows "Login to Admin Panel", while the admin panel shows "Log in". ,, The arrow/login icon present in the Figma button is missing in the admin panel. | https://gyazo.com/edad5393ec2fe0a9d2c59035ece5912 | done
183 | 2026-06-27 | Admin panel(login screen) | Forgot password text mismatch – Figma: "Forgot Password?"; Admin panel: "Forgot your password?" | https://gyazo.com/edad5393ec2fe0a9d2c59035ece5912 | done
184 | 2026-06-27 | Admin panel(login and forget passwordscreen) | Clicking on the Terms of Use and Privacy Policy links does not redirect to any page. The links are non-functional. | https://gyazo.com/edad5393ec2fe0a9d2c59035ece5912,https://gyazo.com/ff2cbf7a0aa5f4eec55128c9887fbea8 |  | figma of privacy policy and terms of use were not provided
185 | 2026-06-27 | Dashboard | "Notification icon" is not funtional | https://gyazo.com/eda841150e31461d0451ab7c8d8f283f | not fixed | need database implementation from app side
186 | 2026-06-27 | Dashboard | Count badge style mismatch – In the Figma design, the user count is displayed inside a light green rectangular box whereas in the admin dashboard it is shown . inside a green pill-shaped badge,. | https://gyazo.com/421c057bb966495f5c6525493bedf16b,https://gyazo.com/bbc8f7b148179040c9a9640e35658df4 | done
187 | 2026-06-27 | Dashboard | Count of content text badge style mismatch – In the Figma design, the user count is displayed inside a light green rectangular box whereas in the admin dashboard it is shown . inside a orange color pill-shaped badge,.and text should be "content moderation" rather then content | https://gyazo.com/8c0c1662ea0696027fd4d77e09244621,https://gyazo.com/bbc8f7b148179040c9a9640e35658df4
188 | 2026-06-27 | left sidebar | all text below all boxes are same colore green in figma but in admin panel there is diffrent color | https://gyazo.com/d20f83850c8a879e7d4c4c815ebd8db7 |  | Not an issue red color gives better visibility
189 | 2026-06-27 | Dashboard | Please confirm this -> Dashboard screen design is diffrent from figma design | https://gyazo.com/765db457c05b54cb83cc8579158af077,https://gyazo.com/d2a3bd796b86c89956b0749e2e33423e,https://gyazo.com/2541cfc4a5b5ef7033105373ea7a0b58 |  | Not an issue , because dashboard is combination of dashboard and analysis section
190 | 2026-06-27 | user screen | Please confirm this -> USER screen design is diffrent from figma design | https://gyazo.com/9cc7577097abb22018d0c645469f2bae,https://gyazo.com/23d30f5364e7d59bc388c86c82d9f02f |  | only two columns are extra date joined and plan
191 | 2026-06-27 | Report screen | "Export CSV " AND "Export Pdf" field qre not working when click | https://gyazo.com/6d3d9d54c02ac212d83ce8029acef3a6 |  | Report section is yet to implement from app side
192 | 2026-06-27 | Report screen | on search input " search icon overlaps on text | https://gyazo.com/6d3d9d54c02ac212d83ce8029acef3a6
193 | 2026-06-27 | Report screen | "dd/mm/yyyy" functionality once check not working propely | https://gyazo.com/6d3d9d54c02ac212d83ce8029acef3a6
194 | 2026-06-27 | Report screen | There are " a green and purple circle visible in figma front of text inside "resolution history" but in admin panel not | https://gyazo.com/1e41f9bdab982c9385777db18a117507,https://prnt.sc/ucfdtx-aC3Ip
195 | 2026-06-27 | Report screen | "admin notes" box inside a gray color box in figma but in admin panel not | https://prnt.sc/ucfdtx-aC3Ip
196 | 2026-06-27 | Report screen | "marked as resolved", Escalate, Dismiss report, save notes - > all buttons are not working | https://prnt.sc/ucfdtx-aC3Ip
197 | 2026-06-27 | Subscription plan | When tried to modify any plan its not modifed after creating a new plan once check on subscription plan screen | https://gyazo.com/d5c30f686d2d242183b4312f08a6e99d
198 | 2026-06-27 | Subscription plan | in "plan points" box when goto subscriptio -> plan -> modify any plan -> plan point box -> when goes to delete icon it goes unvisible but gets deleted when clicking | https://gyazo.com/97adea07aec9353700ad041946815ef3
199 | 2026-06-27 | Subscription plan | when clicking goto -> Action column -> clicking any of "Manage" -> not working | https://prnt.sc/Leo6ZrgbCdlE |  | Not an issue , manage will show data at the end of the page
200 | 2026-06-27 | Subscription plan | subscription details section design not matched with figma (progress green line visible wirh a teat 38% used , buttons text are in one line in figma, and there are only one arrow in figma in upgrade box in figma but in admin panel not ) | https://gyazo.com/7f1d83fc38658287eaf72552ae19807c
201 | 2026-06-27 | Content | Content moderation scrren design in admin panel is diffrent from figma(heading diffrent, below heading text deiffrent, columns name is diffrent,) | https://gyazo.com/e436338acb35ae4c7324850689af7c67
202 | 2026-06-27 | Content -> view content | "heading is missing on view content screen on admin panel | https://gyazo.com/d8fa2998f50b192bc09aa0cf97cde4c1
203 | 2026-06-27 | Sidebar | sidebar is not same design for all scrren on some screen "Analyticls" field is missing(should be same for all screens as per figma design) | https://gyazo.com/f9690033d17a56f38d0d2e200d102d01
204 | 2026-06-27 | Top bar | "super admin" and "notification " icon is diffrent in admin panel from figma design | https://gyazo.com/3673133868e264a9c0bfc284eecb16e3
205 | 2026-06-27 | Content-> View any content click | "content information " and " moderation action" boxes should be on same level in admin panle(horizontally) | https://gyazo.com/d8fa2998f50b192bc09aa0cf97cde4c1
206 | 2026-06-27 | Content-> View any content click | IN "AI Response box" -> should be in gray background as per figma design | https://gyazo.com/d8fa2998f50b192bc09aa0cf97cde4c1
207 | 2026-06-27 | Content-> View any content click | in "Islamic References box" texts are inside a lignt green box in figma but not in admin panel | https://gyazo.com/c701e9cb78d50d3a1a3d631d896c8eb4
208 | 2026-06-27 | Content-> View any content click | in "Moderation History" box time format is not matched with figma design | https://gyazo.com/c701e9cb78d50d3a1a3d631d896c8eb4
209 | 2026-06-27 | Settings | Settings screen design does not matched with figma design check all boxes design | https://gyazo.com/2cdc2253054e1b45e340d0dca76af0be
210 | 2026-06-27 | Sidebar -> click on subscription arrow | when againg click on subscription arrow is not working | https://gyazo.com/fdb143f58922f623037a82cd80c678f3
211 | 2026-06-27 | Analytics screen | Analytics screen is missing on admin panel not visible on sidebar
212 | 2026-06-27 | users | "joining date of user is incorrect as (akansha singh name account created today and joining on date is visible 25 may ) | https://gyazo.com/4642314f27c872f1bb80bdca9969cf18
213 | 2026-06-27 | users | for all users "status is visible "Active" | https://gyazo.com/4642314f27c872f1bb80bdca9969cf18
214 | 2026-06-27 |  | Total users are not updating propely in card it showing diffrent and in sidebar diffrent | https://prnt.sc/MLRrLBEUQTaG
215 | 2026-06-27 |  | "view all "link is not clickable on dashborad screen | https://prnt.sc/XNsOBdauH2uO
216 | 2026-06-27 | Dashboard | After interacting with the chatbot and refreshing the admin dashboard, only the Messages Today card updates. The following dashboard metrics do not change: Total Users Active Users Total Sessions Total Tokens Used Total Billing Cost | https://prnt.sc/X9E8Ex4PXMT1
217 | 2026-06-27 | Dashboard | "Active user" Graph is not visible and not functional on dashboard | https://prnt.sc/1j62ebRUQwJe
218 | 2026-06-27 | User | Flagging a user does not update user status or dashboard counters | https://prnt.sc/V1ylQh9_PynH
219 | 2026-06-27 | User | "I can see the 'Suspended Users' card on the User Management page, but I couldn't find any option to suspend a user. | https://prnt.sc/V1ylQh9_PynH
220 | 2026-06-27 | User | the Active count also does not decrease. | https://prnt.sc/V1ylQh9_PynH
221 | 2026-06-27 | Subscription management | The summary cards on the Subscription Management page are not updating after subscription-related changes. The following cards remain unchanged after refreshing the page: Total Subscribers Premium Plans Monthly Revenue Expiring Soon | https://prnt.sc/b5APRZyh7Rov
|  | Subscription management | When clicking on "Modify" and try to enable a plan and and then save changes , changes are not saving ,(not able to identify "Active Live Tiers and "Disable Tiers" ) | https://gyazo.com/72f72047ccab8654e83807aab6111420