## Jira (7)
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Labels | Description | Environment | Watchers | Watchers | Watchers Id | Watchers Id | Log Work | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Î£ Original Estimate | Î£ Remaining Estimate | Î£ Time Spent | Security Level | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Outward issue link (Blocks) | Custom field (Development) | Custom field (Flagged) | Custom field (Issue color) | Custom field (Rank) | Sprint | Custom field (Start date) | Custom field (Story point estimate) | Custom field (Team) | Custom field (Vulnerability) | Comment | Comment | Status Category | Status Category Changed
Register API returns 500 error even though user data is saved successfully; Email OTP API also returns 500 | SCRUM-167 | 10826 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2026-01-07 19:14 | 2026-01-30 11:05 | 2026-01-13 22:25 |  |  | 0 |  | While testing the *Register API*, the API returns *500 Internal Server Error*, but *user data is successfully saved in the database and visible in the admin panel*. Because of the incorrect response, the *Email OTP API also returns 500*, which blocks email verification and further authenticated API testing. h3. *API Endpoint* {{POST /register/}} h3. *Request Body* * user_type: {{individual}} * first_name: {{varsha}} * last_name: {{bansal}} * email: {{bansalvarsha2525@gmail.com}} * phone: {{7014738644}} * password: {{Varsha@2503}} * business_name: {{individual}} * gst_number: {{08ABCDE1234F1Z5}} * pan_number: {{ABCDE1234F}} * document_type: {{pan}} * document_file: {{IT-BOLT.pdf}} * gstin_doc: {{IT-BOLT.pdf}} * pan_doc: {{IT-BOLT (1).pdf}} * country: {{IN}} * referral_code: _(optional / null)_ ---- h3. *Expected Result* * API should return *201 Created* with a valid JSON response. * User should be registered successfully. ---- h3. *Actual Result* * API returns *500 Internal Server Error*. * Despite the error, user data is successfully saved and visible in the admin panel. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000zj: | Testing | [6 empty] | In Progress | 2026-01-30 11:05
UnicodeDecodeError when uploading documents in Register API | SCRUM-166 | 10793 | Story | To Do | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2026-01-03 11:46 | 2026-01-03 11:46 | 2026-01-31 10:41 |  |  | 0 |  | *API:* POST /api/register/ *Steps to Reproduce:* # Call register API with multipart/form-data # Upload PDF files in {{gstin_doc}}, {{pan_doc}}, {{document_file}} # Submit request *Expected Result:* User should be registered successfully and API should return JSON response. *Actual Result:* Request URL [http://127.0.0.1:8000/api/register/¦http://127.0.0.1:8000/api/register/] Server response Code Details 500 Undocumented Error: Internal Server Error Response body Download UnicodeDecodeError at /api/register/ 'utf-8' codec can't decode byte 0xe2 in position 1: invalid continuation byte Request Method: POST Request URL: [http://127.0.0.1:8000/api/register/¦http://127.0.0.1:8000/api/register/] Django Version: 4.2.25 Python Executable: /home/varshabansal25/.venvs/byto_env/bin/python3 API crashes with UnicodeDecodeError while rendering response. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000zb: | Testing | [6 empty] | To Do | 2026-01-03 11:46
Inconsistent referral code validation: User registers successfully but API returns error when referral code is provided | SCRUM-165 | 10760 | Story | To Do | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-20 19:46 | 2025-12-20 19:46 | 2025-12-22 19:33 |  |  | 0 |  | While testing the {{POST /api/register-with-referral/}} API, inconsistent behavior is observed based on referral code usage. When the API is called *without a referral code*, the user is registered successfully and a proper success response is returned. However, when the API is called *with a referral code*, the user is still created in the database, but the API response incorrectly returns an error message stating â€œInvalid referral codeâ€ with an incorrect HTTP status. h3. *Request Payloads* *Without referral code* {noformat}{ "username": "test_user_no_ref", "password": "Test@123" } {noformat} *With referral code* {noformat}{ "username": "sharmaaji_27", "password": "Varsha@2503", "referral_code": "8c852a4b" } {noformat} ---- h3. *Actual Result* *Without referral code* * User registered successfully * Correct success response returned *With referral code* * User created successfully in database * API response: {noformat}{ "status": 400, "data": null, "message": "Invalid referral code." } {noformat} * HTTP Status Code returned: *200 OK* ---- h3. *Expected Result* * API behavior should be consistent * If referral code is valid: ** User should be registered ** HTTP status should be *201* ** Success message should be returned * If referral code is invalid: ** User should not be created ** HTTP status should be *400* ** Appropriate error message should be returned |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000z3: | Testing | [6 empty] | To Do | 2025-12-20 19:46
Re-arrange Swagger APIs â€“ Common Module | SCRUM-164 | 10727 | Story | In Progress | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  |  |  | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-15 10:51 | 2025-12-21 18:27 |  |  |  | 0 |  | Currently, the Swagger API documentation contains APIs from multiple roles (Customer, Partner, Admin) mixed together. Several APIs are shared across multiple roles and should be grouped under a dedicated "Common" module to improve clarity and navigation. The Common module includes APIs used by all or multiple roles, such as configuration, support, locations, notifications, masked calls, and general utilities. Scope â€“ Common APIs: # App Configuration & Settings #* GET /app/config/ â€“ Retrieve application configuration # Advertisements & Items #* GET /api/ads/ â€“ Fetch advertisements #* GET /api/items/{id}/ â€“ Get item details #* GET /api/createitems/ â€“ List items #* POST /api/createitems/ â€“ Create new items #* PUT /api/items/{id}/ â€“ Update item #* DELETE /api/items/{id}/ â€“ Delete item # Load Types & Loading Details #* GET /create-load-types/ â€“ List load types #* POST /create-load-types/ â€“ Create load type #* GET /load-types/{id}/ â€“ Retrieve load type #* PUT /load-types/{id}/ â€“ Update load type #* DELETE /load-types/{id}/ â€“ Delete load type #* GET /create-loading-details/ â€“ List loading details #* POST /create-loading-details/ â€“ Create loading detail #* GET /loading-details/{id}/ â€“ Retrieve loading detail #* PUT /loading-details/{id}/ â€“ Update loading detail #* DELETE /loading-details/{id}/ â€“ Delete loading detail # Locations #* GET /locations/ â€“ List locations #* POST /locations/add/ â€“ Add a new location #* DELETE /locations/delete/ â€“ Delete a location # Support & Tickets #* GET /support/faqs/ â€“ Retrieve FAQs #* GET /support/contact-info/ â€“ Get support contact info #* POST /support/escalate/ â€“ Escalate support #* GET /support/chats/ â€“ Retrieve support chats #* POST /support/chat/message/ â€“ Send support chat message #* GET /support/ai-assistant/ â€“ AI assistant queries #* POST /support/ai-assistant/ â€“ AI assistant actions #* GET /support-tickets/ â€“ List support tickets #* POST /support-tickets/ â€“ Create support ticket #* GET /support-tickets/{id}/ â€“ Get ticket details #* PUT /support-tickets/{id}/ â€“ Update ticket #* PATCH /support-tickets/{id}/ â€“ Partial update #* DELETE /support-tickets/{id}/ â€“ Delete ticket # Notifications & Push #* GET /notifications/ â€“ Fetch notifications #* GET /notifications/newest-first/ â€“ Notifications sorted by newest #* GET /notifications/oldest-first/ â€“ Notifications sorted by oldest #* GET /notifications/paginated/ â€“ Paginated notifications #* GET /notifications/timeline/ â€“ Notifications timeline #* PATCH /notifications/{id}/read/ â€“ Mark notification as read #* POST /notifications/mark-all-read/ â€“ Mark all notifications as read #* POST /push-notification/ â€“ Send push notification # Masked Calls & Communication #* POST /masked/sessions/ â€“ Create masked session #* GET /masked/sessions/{session_id}/logs/ â€“ Get session logs #* POST /masked/sessions/{session_id}/revoke/ â€“ Revoke masked session #* POST /masked/webhook/twilio/ â€“ Twilio webhook for masked sessions # Referral & Languages #* GET /referral/summary/ â€“ Fetch referral summary #* GET /list-languages/ â€“ Fetch available languages |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000yv: | Testing | [6 empty] | In Progress | 2025-12-21 18:27
Re-arrange Swagger APIs â€“ Admin Panel Module | SCRUM-163 | 10726 | Story | In Progress | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  |  |  | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-15 10:49 | 2025-12-21 18:26 |  |  |  | 0 |  | Currently, Swagger API documentation mixes Customer, Partner, and Admin APIs, making it difficult to identify which APIs are Admin-only. To improve clarity and maintainability, all Admin-level APIs should be grouped under a dedicated "Admin Panel" module in Swagger. This module includes APIs for managing disputes, SOS alerts, driver document verification, trip logs, and administrative actions such as exports and reports. Scope â€“ Admin Panel APIs: # Partner Disputes Management #* GET /admin/disputes/ â€“ List all disputes #* PUT /admin/disputes/{id}/ â€“ Update dispute #* PATCH /admin/disputes/{id}/ â€“ Partial update dispute # SOS (Emergency) Management #* GET /admin/sos/active â€“ List active SOS alerts #* POST /admin/sos/{alert_id}/force-close â€“ Force-close an SOS alert #* POST /admin/sos/{alert_id}/takeover â€“ Takeover an SOS alert # Driver Document Verification #* GET /driver-documents/{id}/verify/ â€“ Get document verification details #* POST /driver-documents/{id}/verify/ â€“ Approve or reject driver documents (Admin only) #* GET /driver-documents/access-history/ â€“ View document access history # Trip Logs Management #* GET /trip-logs/ â€“ List all trip logs #* GET /trip-logs/export/ â€“ Export trip logs (CSV/JSON) #* GET /trip-logs/{id}/ â€“ Retrieve specific trip log #* POST /trip-logs/{id}/verify/ â€“ Verify integrity of a trip log # Document Verification (Common Admin Tasks) #* PATCH /verify-doc/ â€“ Partial update to verify documents # Business Bookings Exports #* POST /business/bookings/export/ â€“ Export business booking data #* GET /business/bookings/history/ â€“ Fetch business booking history # Dispute Management for Partners #* GET /disputes/ â€“ List disputes #* POST /disputes/ â€“ Create dispute #* GET /disputes/{id}/ â€“ Retrieve dispute details #* PUT /disputes/{id}/ â€“ Update dispute #* PATCH /disputes/{id}/ â€“ Partial update dispute |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000yn: | Testing | [6 empty] | In Progress | 2025-12-21 18:26
Re-arrange Swagger APIs â€“ Partner Module | SCRUM-162 | 10725 | Story | In Progress | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  |  |  | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-15 10:47 | 2025-12-21 18:26 |  |  |  | 0 |  | Currently, Swagger API documentation contains APIs from multiple modules mixed together. All Partner/Driver-related APIs should be grouped under a dedicated "Partner" module for better clarity and maintainability. This module includes APIs used by Partner or Driver apps for managing bookings, trips, earnings, documents, vehicles, and analytics. Scope â€“ Partner Module APIs: # Driver Bookings APIs #* POST /api/bookings/driver/accept/ â€“ Accept a booking #* POST /api/bookings/driver/arrived/ â€“ Mark driver as arrived #* POST /api/bookings/driver/cancel/ â€“ Cancel driver booking #* POST /api/bookings/driver/reject/ â€“ Reject a booking #* GET /api/bookings/driver/scheduled-trips/ â€“ List scheduled trips #* POST /api/bookings/driver/start/ â€“ Start a trip #* POST /api/bookings/driver/verify-end/ â€“ Verify trip end #* GET /bookings/driver-dashboard/ â€“ Fetch driver dashboard # Driver Communication APIs #* GET /driver/chat/history/ â€“ Get driver chat history #* POST /driver/chat/send/ â€“ Send chat message #* POST /driver/initiate/call/ â€“ Start masked call #* POST /driver/release/call/ â€“ Release masked session #* GET /driver/quick-replies/ â€“ Get quick replies for chat #* GET /driver/twilio/twiml/ â€“ Fetch Twilio TwiML for call # Driver Documents APIs #* GET /driver/documents/ â€“ List driver documents #* POST /driver/documents/ â€“ Add new driver document #* PUT /driver/documents/ â€“ Update driver document #* GET /driver-documents/access-history/ â€“ Document access history #* GET /driver-documents/{id}/download/ â€“ Download document #* GET /driver-documents/{id}/verify/ â€“ Verify document (Admin only) #* POST /driver-documents/{id}/verify/ â€“ Approve/reject document (Admin only) # Earnings & Trips APIs #* GET /earnings/dashboard/ â€“ Driver earnings dashboard #* GET /trips/{booking_id}/fare/ â€“ Get trip fare #* POST /trips/{booking_id}/feedback/ â€“ Submit trip feedback #* POST /trips/{booking_id}/helper/ â€“ Add helper for trip #* POST /trip/resend-otp/ â€“ Resend OTP for trip #* GET /tripsummary/{booking_id}/ â€“ Get trip summary # Vehicle & Truck Management APIs #* GET /vehicle-types/ â€“ List vehicle types #* POST /vehicle/register/ â€“ Register a vehicle #* GET /vehicle/{id}/status/ â€“ Get vehicle status #* POST /vehicle/{vehicle_id}/upload-document/ â€“ Upload vehicle document #* GET /truck-driver-details/{id}/ â€“ Fetch truck-driver details #* GET /trucks/ â€“ List trucks #* POST /trucks/ â€“ Add new truck #* GET /trucks/{id}/ â€“ Get truck details #* PUT /trucks/{id}/ â€“ Update truck #* DELETE /trucks/{id}/ â€“ Delete truck # Partner Analytics APIs #* GET /partner/analytics/ â€“ Partner analytics dashboard #* GET /partner/analytics/export/ â€“ Export analytics report # Partner Authentication APIs #* POST /partner/request-otp/ â€“ Request OTP for login #* POST /partner/verify-otp/ â€“ Verify OTP |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000yf: | Testing | [6 empty] | In Progress | 2025-12-21 18:26
Re-arrange Swagger APIs â€“ Customer Module | SCRUM-161 | 10724 | Story | In Progress | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  |  |  | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-15 10:44 | 2025-12-21 18:26 |  |  |  | 0 |  | Currently, the Swagger API documentation lists APIs from multiple modules together, making it difficult to identify which APIs are specifically for the Customer-facing application. To improve clarity and usability, all APIs used by the Customer app should be grouped under a dedicated "Customer" module. This module should include the following APIs: # *Booking APIs* #* Create booking: POST /create-bookings/ #* Active bookings: GET /bookings/active/ #* Booking history: GET /bookings/history/ #* Track booking: GET /bookings/{id}/track/ #* Cancel booking: POST /bookings/cancel/ #* Book for others: POST /bookings/bookforothers/ #* Booking reminders: POST /bookings/{id}/reminder/ #* Booking location updates (driver-related, if visible to customer): POST /bookings/{booking_id}/location/ #* Latest location: GET /bookings/{booking_id}/location/latest/ #* SOS APIs for booking: POST /bookings/{booking_id}/sos/start/, PATCH /bookings/{booking_id}/sos/ping/, PUT /bookings/{booking_id}/sos/close/ #* Status timeline: GET /bookings/{booking_id}/status-timeline/ #* Status update: PATCH /bookings/{booking_id}/status/ # *Payment & Wallet APIs* #* Create payment order: POST /payment/create-order/ #* Fare summary: POST /payment/fare-summary/ #* QR payment status: GET /payment/qr-status/ #* Driver UPI QR payment: POST /payment/qr/driver/ #* Payment Razorpay webhook: POST /payment/razorpay-webhook/ #* Wallet APIs: #** Wallet balance: GET /wallet/ #** Deduct amount: POST /wallet/deduct/ #** List saved payment methods: GET /wallet/add/ #** Wallet top-up: POST /wallet/add/ #** Delete saved payment method: DELETE /wallet/add/ #** Wallet verification webhook: POST /wallet/verify/ # *User Profile & Address APIs* #* User profile: GET /user/profile/ #* Update profile: PATCH /updateprofile/, PUT /updateprofile/, POST /updateprofile/ #* Emergency contacts: GET /profile/emergency-contacts/, PUT /profile/emergency-contacts/ #* User addresses: GET /user/addresses/, POST /user/addresses/, GET /user/addresses/{address_id}/, PUT /user/addresses/{address_id}/, DELETE /user/addresses/{address_id}/ #* User preferences: GET /user/preferences/, PUT /user/preferences/ #* User language settings: PATCH /user/language/ #* User verification status: GET /user/verification-status/ #* User settings: PATCH /user/settings/ #* Legal consent: POST /user/legal-consent/ #* Delete user: DELETE /user/delete/ # *Authentication & Registration APIs* #* Login: POST /login/ #* Registration: POST /register/, POST /register-with-referral/ #* Social login: POST /dj-rest-auth/facebook/, POST /dj-rest-auth/google/ #* OTP APIs: #** Send email OTP: POST /send-email-otp/, Verify email OTP: POST /verify-email-otp/ #** Send OTP: POST /send-otp/, Verify OTP: POST /verify-otp/ #** Login OTP: POST /send-login-email-otp/, POST /send-login-phone-otp/, POST /verify-login-email-otp/, POST /verify-login-phone-otp/ #* Password reset: #** Request OTP: POST /request-otp/ #** Verify OTP & reset password: POST /verify-otp-reset-password/ # *Notifications APIs* #* Fetch notifications: GET /notifications/, GET /notifications/newest-first/, GET /notifications/oldest-first/, GET /notifications/paginated/, GET /notifications/timeline/ #* Mark as read: PATCH /notifications/{id}/read/, POST /notifications/mark-all-read/ # *Feedback & Ratings* #* Feedback details: GET /feedback/detail/{booking_id}/ #* Submit feedback: POST /feedback/{booking_id}/ #* Driver rating: POST /give_rating_to_driver/ #* Passenger ratings: GET /passenger-ratings/, POST /passenger-ratings/, GET /passenger-ratings/{id}/ # *Promotions & Discounts* #* Apply discount: POST /discounts/apply/{booking_id}/ #* Validate discount: POST /discounts/validate/ #* Driver promotions (visible to customer if applicable): GET /promotions/driver/ # *Suggestions & Rebook* #* Get rebook suggestions: GET /suggestions/rebook/ #* Refresh suggestions: POST /suggestions/rebook/refresh/ #* Rebook suggestion: POST /suggestions/{suggestion_id}/rebook/ |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000y7: | Testing | [6 empty] | In Progress | 2025-12-21 18:26
GET /drivers/{driver_id}/bonuses/ API returns 404 due to missing bonus records | SCRUM-150 | 10649 | Story | To Do | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-08 11:37 | 2025-12-08 11:37 | 2026-02-10 12:33 |  |  | 0 |  | When attempting to fetch bonus records for a driver using the GET API {{/drivers/{driver_id}/bonuses/}}, the API returns a 404 response with the message: {noformat}{ "message": "No bonus records found for this driver." } {noformat} Upon checking the Django admin panel, there is *no model/table for driver bonuses*, and no data exists for any driver. Since there is no API to create bonus records, the GET request cannot return any results. *Expected Result:* * Either return an empty list if no bonus records exist: {noformat}{ "code": 200, "data": [], "message": "No bonus records found for this driver." } {noformat} * Or allow creation of bonus records via an API so that the GET request can fetch real data. *Actual Result:* * API returns 404 with the message: {{"No bonus records found for this driver."}} * No table/model exists for driver bonuses in the database. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000vr: | Testing | [6 empty] | To Do | 2025-12-08 11:37
POST /api/vehicle/register/ returns 400 error asking for vehicle_photo even though the request body in Swagger shows only truck_type and vehicle_number. | SCRUM-149 | 10648 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-08 11:10 | 2025-12-11 12:12 |  |  |  | 0 |  | While testing the *Vehicle Register API (POST /api/vehicle/register/)* in Swagger, the API returns a *400 Bad Request* error. The error message indicates: {noformat}"vehicle_photo": ["No file was submitted."] {noformat} However, the API documentation/model in Swagger only shows these required fields: {noformat}{ "truck_type": 1, "vehicle_number": "RJ14AB5555" } {noformat} There is no mention that *vehicle_photo is required* or that the request should be sent as multipart/form-data. This causes confusion and makes it impossible for QA to successfully register a vehicle. Set request body to JSON: {noformat}{ "truck_type": 1, "vehicle_number": "RJ14AB5555" }{noformat} h2. *Actual Result* API returns *400 Bad Request*: {noformat}{ "vehicle_photo": [ "No file was submitted." ] }{noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000vj: | Testing |  |  |  |  | 11/Dec/25 12:12 PM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;RETEST PASSED - DONE |  | In Progress | 2025-12-11 12:12
Swagger UI does not allow file upload for /bookings/{booking_id}/upload_signature/ | SCRUM-148 | 10615 | Story | Testing | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-05 10:44 | 2025-12-06 23:45 |  |  |  | 0 |  | * The endpoint {{/bookings/{booking_id}/upload_signature/}} expects a *multipart/form-data* request containing a driver signature file. * In Swagger UI, the request body shows only an empty JSON ({{{}}}) and *does not provide any option to upload a file*. * Sending empty JSON results in a 400 error: {{"Signature file is required."}} * Because of this, QA *cannot test signature upload via Swagger*. *Steps to Reproduce:* # Open Swagger UI for {{/bookings/{booking_id}/upload_signature/}}. # Click â€œTry it outâ€. # Observe that there is *no field to select/upload a signature file*. # Send request with {{{}}} â†’ API returns 400 error: {{"Signature file is required."}} *Expected Result:* * Swagger UI should allow file selection/upload for the signature. *Actual Result:* * Swagger shows only empty JSON, and QA cannot upload signature. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000vb: | Testing | [6 empty] | In Progress | 2025-12-06 23:45
Swagger UI does not allow file upload for /bookings/{booking_id}/upload_proof/ | SCRUM-147 | 10614 | Story | Testing | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-05 10:42 | 2025-12-06 23:45 | 2025-12-22 19:30 |  |  | 0 |  | * The endpoint {{/bookings/{booking_id}/upload_proof/}} expects *multipart/form-data* with a file (proof image) to be uploaded. * In Swagger UI, the request body shows only an empty JSON ({{{}}}) and *does not provide any option to select/upload a file*. * Because of this, QA *cannot test file upload via Swagger*. *Steps to Reproduce:* # Open Swagger UI for {{/bookings/{booking_id}/upload_proof/}}. # Click â€œTry it outâ€. # Observe that there is *no field to upload a file*. # Sending empty JSON {{{}}} results in error: {{"Proof file is required."}} *Expected Result:* * Swagger UI should allow file selection/upload for the {{file}} parameter, so QA can test uploading proof. *Actual Result:* * Swagger only shows an empty JSON {{{}}} â†’ cannot upload file. * API returns 400 error: {{"Proof file is required."}} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000v3: | Testing | [6 empty] | In Progress | 2025-12-06 23:45
Unable to upload vehicle photo using /vehicle/register/ API in Swagger | SCRUM-146 | 10581 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-04 20:56 | 2025-12-11 07:31 |  |  |  | 0 |  | While testing the Vehicle Registration API (/vehicle/register/) in Swagger, the "vehicle_photo" field cannot be uploaded. The API requires a file for "vehicle_photo", but Swagger does not provide an option to select/upload a file. As a result, the API returns a 400 Bad Request error. Steps to Reproduce: # Open Swagger UI for /vehicle/register/ endpoint. # Fill in truck_type and vehicle_number fields. # Attempt to send the request without vehicle_photo. # Observe the response. Actual Response: { "vehicle_photo": ["No file was submitted."] } Expected Response: { "truck_type": 1, "vehicle_number": "MH12AB1234", "vehicle_photo": "<uploaded file URL>" } Endpoint URL: POST [http://127.0.0.1:8000/api/vehicle/register/¦http://127.0.0.1:8000/api/vehicle/register/] Issue Type: Bug / Swagger UI not allowing file upload for vehicle_photo. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000uv: | [7 empty] | In Progress | 2025-12-11 07:31
502 Bad Gateway error on Wallet Top-up API (/wallet/add/) with Razorpay | SCRUM-145 | 10580 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | sandip rathod | 712020:12abd38d-19a9-43ea-90ab-8c52d262931d | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-12-04 20:40 | 2025-12-12 10:15 |  |  |  | 0 |  | While testing the Wallet Top-up API, attempting to initiate a Razorpay payment link fails with a {{502 Bad Gateway}} error. This issue occurs even with valid input and proper authentication. The error seems related to Razorpay integration *Steps to Reproduce:* # Authenticate as a valid user. # Make a POST request to {{/wallet/add/}} with the following payload: {noformat}{ "amount": "500", "save_method": false } {noformat} # Include valid Authorization header and CSRF token. # Execute the API request. *Actual Response:* * *HTTP Code:* 502 * *Response Body:* {noformat}{ "code": 502, "error": "Invalid request to Razorpay" } {noformat} *Expected Response:* * *HTTP Code:* 200 * *Response Body:* {noformat}{ "payment_link": "string", "payment_link_id": "string", "reference_id": "string", "amount": 500, "currency": "INR", "key_id": "string" } {noformat} *Endpoint URL:* {{POST http://127.0.0.1:8000/api/wallet/add/}} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000un: | Testing | [6 empty] | In Progress | 2025-12-11 13:39
Support Contact Info API fails with â€œsettings.GENERAL attribute missingâ€ error in backend. | SCRUM-144 | 10547 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | sandip rathod | 712020:12abd38d-19a9-43ea-90ab-8c52d262931d | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-14 12:19 | 2025-12-15 18:07 |  |  |  | 0 |  | h1. *API Endpoint* {noformat}GET /support/contact-info/{noformat} FULL REQUESTED URL: {{http://127.0.0.1:8000/api/support/contact-info/}} h1. *Request Body* h1. _This API is GET, so no body is required_ {noformat}N/A (GET request â€“ no request body){noformat} Expected RESPONSE : API should return valid support contact details without any errors. ACTUAL RESULT: ¦500 {noformat}Undocumented{noformat}¦Error: Internal Server Error h5. Response body {color:#ffffff}Download{color} {noformat}AttributeError at /api/support/contact-info/ 'Settings' object has no attribute 'GENERAL' Request Method: GET Request URL: http://127.0.0.1:8000/api/support/contact-info/{noformat}¦ |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000uf: | Testing | [6 empty] | In Progress | 2025-12-11 13:34
Payment APIs cannot be tested because Booking Location Create API is failing (no booking_id available) | SCRUM-143 | 10546 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Vaibhav Gupta | 712020:26cd3149-0731-4147-b732-c311f2a951df | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-14 11:37 | 2025-12-05 11:47 |  |  |  | 0 |  | API ENDPOINT: {color:#ffffff}*POST*{color}*/payment/create-order/* METHOD:POST FULL REQUESTED URL: {{http://127.0.0.1:8000/api/payment/create-order/}} h3. *Request Body Used (example):* {noformat}{ "booking_id": 1 }{noformat} EXPECTED RESPONSE: 200 â€“ ¦Success¦ ACTUAL RESULT: API returns *400 / 500 error* due to missing or invalid {{booking_id}} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [13 empty] | SCRUM-130 |  |  |  | 0¦i000u7: | Testing |  |  |  |  | 05/Dec/25 11:47 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;RETEST FAILED |  | In Progress | 2025-11-25 23:55
POST /passenger-ratings/ API cannot be fully tested due to Booking Location Create API failure | SCRUM-142 | 10545 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Vaibhav Gupta | 712020:26cd3149-0731-4147-b732-c311f2a951df | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-14 11:26 | 2025-11-27 23:54 |  |  |  | 0 |  | We are unable to fully test the {{POST /passenger-ratings/}} API because it depends on a valid trip created via the Booking Location API ({{/booking-location-create/}}). Since the Booking Location API is currently failing, we do not have valid {{trip_id}} to submit ratings. *Requested Body (Dummy/Test Data):* {noformat}{ "trip": 123, // Use a dummy trip ID (integer) "stars": 5, // Number of stars (1-5) "tags": ["friendly"], // Tags describing the passenger "comments": "Test rating" // Comments for the passenger }{noformat} *Expected Result:* * API should return {{201 Created}} with the newly created PassengerRating object. * Response should include: {{id}}, {{rating_id}}, {{trip}}, {{passenger}}, {{driver}}, {{stars}}, {{tags}}, {{comments}}, {{created_at}}, and {{updated_at}}. *Actual Result:* * Unable to test because {{trip_id}} is not available due to Booking Location API failure. * API returns {{400 Bad Request}} if a dummy or invalid {{trip_id}} is used. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [13 empty] | SCRUM-141 |  |  |  | 0¦i000tz: | Testing | [6 empty] | In Progress | 2025-11-25 23:55
POST /masked/sessions API cannot be tested â€“ trip_id unavailable due to booking-location-create API failure | SCRUM-141 | 10544 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Vaibhav Gupta | 712020:26cd3149-0731-4147-b732-c311f2a951df | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-14 11:19 | 2025-11-27 23:54 |  |  |  | 0 |  | The *POST /masked/sessions/* API cannot be tested because the *trip_id* required for the request is not available. The trip_id is generated only after successfully creating a booking using the *POST /booking-location-create/* API. REQUESTED BODY: { "trip_id": "generated_trip_id_from_booking", "driver_id": 123, "passenger_id": 456, "driver_number": "+911234567890", "passenger_number": "+919876543210", "provider": "twilio" } h3. *Expected Result* * A new masked session should be created. * The API should return *HTTP 201 Created* with a response containing: ** {{id}}: unique session ID ** {{trip_id}}: the same trip_id from booking ** {{driver_id}} and {{passenger_id}} ** {{masked_number}}: Twilio virtual number allocated ** {{status}}: e.g., "active" ** {{provider}}: "twilio" ** {{started_at}}, {{ended_at}}, {{grace_minutes}} ACTUAL RESULT: ¦500 {noformat}Undocumented{noformat}¦Error: Internal Server Error¦ |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [10 empty] | SCRUM-142 |  |  | SCRUM-130 |  |  |  | 0¦i000tr: | Testing | [6 empty] | In Progress | 2025-11-26
[BUG] Vehicle Register API - Missing 'vehicle_photo' field in Swagger documentation . | SCRUM-140 | 10511 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-13 13:09 | 2025-12-22 19:29 | 2025-12-22 19:29 |  |  | 0 |  | API ENDPOINT: {color:#ffffff}*POST*{color}*/vehicle/register/* METHOD: POST FULL REQUESTED URL: {{http://127.0.0.1:8000/api/vehicle/register/}} REQUESTED BODY : ACTUAL RESULT: While testing the {{POST /vehicle/register/}} API in Swagger, the request fails with the following error: {noformat}{ "vehicle_photo": ["No file was submitted."] } {noformat} However, the Swagger documentation does not include any field for uploading {{vehicle_photo}}. This makes it impossible to test the API successfully from Swagger as per the provided model. ¦400¦Error: Bad Request h5. Response body {color:#ffffff}Download{color} {noformat}{ "vehicle_photo": [ "No file was submitted." ] }{noformat}¦ EXPECTED RESULT: 201 -API should register the vehicle successfully with the given details and return a {{201 Created}} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000tj: | Testing |  |  |  |  | 22/Dec/25 7:29 PM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;RETESTING DONE |  | In Progress | 2025-11-24 01:28
Download API failing due to missing AES_256_KEY_B64 configuration | SCRUM-139 | 10510 | Story | To Do | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Vaibhav Gupta | 712020:26cd3149-0731-4147-b732-c311f2a951df | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-13 12:45 | 2025-11-13 12:46 | 2025-12-22 19:32 |  |  | 0 |  | API ENDPOINT: {{http://127.0.0.1:8000/api/driver-documents/3/download/}} {color:#ffffff}*GET*{color}*/driver-documents/{id}/download/* Method: GET While testing the {{GET /driver-documents/{id}/download/}} API, a {{500 Internal Server Error}} occurred. The error message indicates a missing encryption key configuration in the backend. *Error message:* ¦Error: Internal Server Error h5. Response body {color:#ffffff}Download{color} {noformat}{ "error": "Could not decrypt or serve file: AES_256_KEY_B64 not set in environment or settings (base64-encoded 32 bytes)." }{noformat}¦ EXPECTED RESULT: 200 -The document should be successfully downloaded. REQUESTED BODY: Only the *path parameter* ({{id}}) and *authorization token* in the headers. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000tb: | Testing | [6 empty] | To Do | 2025-11-13 12:45
500 Internal Server Error on /api/register-with-referral/ due to missing username field | SCRUM-138 | 10477 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | pankajverma3242 | 712020:7e01faa8-9fdb-4b0c-9b25-3c106fd9db4e | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-11 14:26 | 2025-12-05 11:46 |  |  |  | 0 |  | *API Endpoint:* {{POST /api/register-with-referral/}} Full Requested URL: {{http://127.0.0.1:8000/api/register-with-referral/}} *Method:* POST h3. ðŸ”¹ *Request Body Used* { "username": "Varban25", "password": "Varsha@123", "referral_code": "172cec62" } *Content-Type:* {{application/json}} h3. ðŸ”¹ *Expected Response* 201 - User Registered Successfully h3. ðŸ”¹ *Actual Response* Response code: {{500 Internal Server Error}} {noformat}FieldError at /api/register-with-referral/ Cannot resolve keyword 'username' into field. Choices are: assigned_tickets, auth_token, business_profile, cancellation, country, created_at, created_promos, deleted_at, deletion_reason, device_token, documents, email, email_verified, emailaddress, fareestimation, first_login, first_name, groups, id, is_active, is_deleted, is_first_booking_discount_applied, is_staff, is_superuser, language, last_login, last_name, logentry, notifications, partner_bookings, password, phone, phone_verified, profile_image, promousage, razorpaypayment, referral, referral_code, referral_earnings, referral_trip_completed, referrals, referred_by, referred_by_id, saved_locations, savedpaymentmethod, settings, supportchat, supportticket, tripfeedback, updated_at, user_bookings, user_permissions, user_referrer, user_type, verification, wallet, wallettopuprequest Request Method: POST{noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [13 empty] | SCRUM-119 |  |  |  | 0¦i000t3: | Testing |  |  |  |  | 05/Dec/25 11:46 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;RETEST PASSED-DONE |  | In Progress | 2025-11-22 21:42
POST /push-notification/ - API returns 500 Internal Server Error for valid input | SCRUM-137 | 10476 | Story | Testing | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-11 11:44 | 2025-12-02 08:44 |  |  |  | 0 |  | *API Endpoint:* {{http://127.0.0.1:8000/api/push-notification/}} While testing the *POST /push-notification/* API, the server returned a *500 Internal Server Error* even though valid input data and authorization token were used. *Request Body:* { "title": "Test Notification QA", "message": "This is a test notification to verify /notifications/ API.", "type": "general" } h3. *Expected Result:* * API should return: {noformat}{ "message": "Push notification sent successfully." } {noformat} * Status Code: {{200 OK}} h3. *Actual Result:* * API returned * 500 - Internal Server Error * {noformat}{ "error": "Failed to send push notification" } {noformat} *Content-Type:* {{application/json}} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [15 empty] | Impediment |  | 0¦i000sv: | Testing | [6 empty] | In Progress | 2025-11-11 23:49
Fare Estimate API not working due to Booking Location Create API failure â€” returning error related to invalid or missing location ID. | SCRUM-136 | 10475 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Vishal Gupta | 712020:6a83fad8-320c-4532-b1d0-c777f54a24d8 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-11 11:02 | 2025-12-19 00:01 |  |  |  | 0 |  | *API Endpoint:* {{http://127.0.0.1:8000/api/fare-estimate/}} This issue seems to be due to a dependency between the two APIs, where *Fare Estimate* relies on the *SavedLocation* created from *Booking Location Create API*. *Request Body:* { "load_type_id": 1, "origin": "Home", "destination": "Office", "weight": 12.8, "is_peak_hour": false } *Content-Type:* {{application/json}} *Expected Response:* ¦200¦Estimated fare details.¦ Fare Estimate API should return a valid estimated fare based on the provided load type, origin, and destination. *Actual Result:* The API returns a {{400 Bad Request}} response: {noformat}{ "code": 400, "error": { "location": "Invalid location ID(s): No SavedLocation matches the given query." } } {noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000sn: | Testing | [6 empty] | In Progress | 2025-12-11 22:14
POST /bookings/bookforothers/ API - Booking for Others Failed | SCRUM-135 | 10442 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Vishal Gupta | 712020:6a83fad8-320c-4532-b1d0-c777f54a24d8 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-10 14:09 | 2025-12-11 12:11 |  |  |  | 0 |  | Attempted to test the POST API to book a truck for another person, but the API returned a *400 Bad Request* because the booking ID used does not exist. *API Endpoint:* {noformat}POST /bookings/bookforothers/{noformat} *Full URL tested:* {{http://127.0.0.1:8000/api/bookings/bookforothers/}} *Request Body (Sent):* {noformat}{ "booking": 1, "recipient_name": "Rahul Sharma", "recipient_phone": "9876543210" } {noformat} *Expected Response:* {noformat}{ "booking": 1, "recipient_name": "Rahul Sharma", "recipient_phone": "9876543210" } {noformat} *Actual Response:* {noformat}{ "code": 400, "error": { "booking": [ "Invalid pk \"1\" - object does not exist." ] } }{noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [13 empty] | SCRUM-132 |  |  |  | 0¦i000sf: | Testing |  |  |  |  | 11/Dec/25 12:11 PM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;RETEST PASSED - DONE |  | In Progress | 2025-12-11 12:11
Test GET /bookings/{id}/track/ API â€” Track a specific booking by ID | SCRUM-134 | 10441 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Vishal Gupta | 712020:6a83fad8-320c-4532-b1d0-c777f54a24d8 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-10 13:30 | 2025-12-11 11:48 |  |  |  | 0 |  | *Objective:* Verify that the GET {{/bookings/{id}/track/}} API returns tracking details for a specific booking. *Dependency:* This API depends on *POST* {{/create-bookings/}} API to create a valid booking first. h3. *API Endpoint Tested:* {noformat}GET /bookings/{id}/track/ {noformat} *Full URL:* {{http://127.0.0.1:8000/api/bookings/1/track/}} ---- h3. *Request Details:* * *Request Type:* GET * *Parameters:* {noformat}id = 1 // Booking ID to track{noformat} h3. *Actual Response:* * *Status Code:* {{404 Not Found}} * *Response Body:* {noformat}{ "detail": "No Booking matches the given query." }{noformat} h3. *Expected Response:* * *Status Code:* {{200 OK}} ¦Booking tracking details.¦ * *Response Body Example:* {noformat}{ "id": 1, "created_at": "2025-11-10T05:30:42Z", "updated_at": "2025-11-10T10:00:00Z", "scheduled_time": "2025-11-11T10:00:00Z", "original_price": "1200.00", "final_price": "1100.00", "status": "PENDING", "discount_applied": false, "loading_help": true, "weight": 1200, "is_fragile": false, "estimated_arrival_time": "2025-11-11T16:00:00Z", "user": 1, "booking_location": 1, "truck_type": 1, "partner": null, "booking_type": "Scheduled", "load_type": 1, "promo_applied": null, "is_archived": false, "discount_amount": "0.00" }{noformat} |  | varsha bansal | Vishal Gupta | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 712020:6a83fad8-320c-4532-b1d0-c777f54a24d8 | [12 empty] | SCRUM-132 |  |  |  | 0¦i000s7: | Testing |  |  |  |  | 11/Dec/25 11:40 AM;712020:6a83fad8-320c-4532-b1d0-c777f54a24d8;[~accountid:712020:e56a999e-31c2-4566-af9d-0ba62f0ff271] [~accountid:712020:acff4cd7-6975-438e-947b-71ce4c05dddd] it is allready working | 11/Dec/25 11:48 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest passed â€“ DONE | In Progress | 2025-12-11 11:37
Test GET /bookings/active/ API â€” Fetch Active Bookings (Dependent on POST /create-bookings/ API) | SCRUM-133 | 10440 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Vaibhav Gupta | 712020:26cd3149-0731-4147-b732-c311f2a951df | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-10 13:19 | 2025-12-05 11:46 |  |  |  | 0 |  | h3. *API Endpoint Tested:* {noformat}GET /bookings/active/ {noformat} ---- h3. *ðŸ§ Request Details:* *Request Type:* {{GET}} h4. Curl {noformat}curl -X 'GET' \ 'http://127.0.0.1:8000/api/bookings/active/' \ -H 'accept: application/json' \ -H 'Authorization: Bearer eyJhbGciOiJIUzI1NiIsInR5cCI6IkpXVCJ9.eyJ0b2tlbl90eXBlIjoiYWNjZXNzIiwiZXhwIjoxNzYyODM0MTUzLCJpYXQiOjE3NjI3NDc3NTMsImp0aSI6Ijc5OGRhYjYzNzNjNzQyNzJiZjM1OGQ0ODJkYjlkNDBmIiwidXNlcl9pZCI6IjEifQ.iTxuQD96mMu1A8kWUl8yei1TdNKhPz3OAzfwlPXqSzI' \ -H 'X-CSRFTOKEN: 79Ds0xmEgFpm7WbLeZ7zPalnKFxony3m'{noformat} h4. Request URL {noformat}http://127.0.0.1:8000/api/bookings/active/{noformat} h3. *âœ… Expected Response:* * *Status Code:* {{200 OK}} * *Response Body Example:* {noformat}[ { "id": 7, "booking_location_id": 1, "truck_type_id": 1, "booking_type": "Scheduled", "receiver_info": { "name": "Rahul Sharma", "phone": "9876543210", "address": "Plot 23, Vaishali Nagar, Jaipur", "email": "rahul.sharma@example.com" }, "load_type_id": 1, "weight": 1200, "is_fragile": false, "loading_help": true, "status": "Active" } ] {noformat} h3. *Actual Response:* * *Status Code:* {{200 OK}} * *Response Body:* {noformat}[] {noformat} _(Empty list because POST_ {{/create-bookings/}} _API failed earlier)_ |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [13 empty] | SCRUM-132 |  |  |  | 0¦i000rz: | Testing |  |  |  |  | 05/Dec/25 11:46 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;RETEST PASSED-DONE |  | In Progress | 2025-11-25 23:31
â€œBooking Location creation API not saving data â€” causing dependency failure in Create Booking API.â€ | SCRUM-132 | 10439 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Vaibhav Gupta | 712020:26cd3149-0731-4147-b732-c311f2a951df | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-10 12:52 | 2025-12-05 11:46 |  |  |  | 0 |  | h3. ðŸ”¹ API Endpoint {noformat}POST /create-bookings/ {noformat} *Full URL tested:* {{http://127.0.0.1:8000/api/create-bookings/}} ---- h3. ðŸ”¹ Request Headers {noformat}Authorization: Bearer <valid access token> Content-Type: application/json {noformat} ---- h3. ðŸ”¹ Request Body (JSON) {noformat}{ "booking_location_id": 1, "scheduled_time": "2025-11-11T10:00:00Z", "truck_type_id": 1, "booking_type": "Scheduled", "receiver_info": { "name": "Rahul Sharma", "phone": "9876543210", "address": "Plot 23, Vaishali Nagar, Jaipur", "email": "rahul.sharma@example.com" }, "load_type_id": 1, "weight": 1200, "is_fragile": false, "loading_help": true } {noformat} ---- h3. ðŸ”¹ Expected Response *HTTP Status Code:* {{201 Created}} *Expected Output (as per API documentation):* {noformat}{ "id": 1, "user": 1, "booking_location_id": 1, "scheduled_time": "2025-11-11T10:00:00Z", "truck_type_id": 1, "original_price": "1500.00", "final_price": "1500.00", "booking_type": "Scheduled", "receiver_info": { "name": "Rahul Sharma", "phone": "9876543210", "address": "Plot 23, Vaishali Nagar, Jaipur", "email": "rahul.sharma@example.com" }, "load_type_id": 1, "weight": 1200, "is_fragile": false, "loading_help": true } {noformat} ---- h3. ðŸ”¹ Actual Response *HTTP Status Code:* {{400 Bad Request}} *Response Body:* {noformat}{ "booking_location_id": [ "Invalid pk \"1\" - object does not exist." ] }{noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [10 empty] | SCRUM-133 | SCRUM-134 | SCRUM-135 |  |  |  |  | 0¦i000rr: | Testing |  |  |  |  | 05/Dec/25 11:46 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;RETEST PASSED-DONE |  | In Progress | 2025-11-25 23:18
[BUG] GET /booking-location-create/ API returns empty list even after adding pickup & dropoff locations | SCRUM-131 | 10438 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-10 12:26 | 2025-12-03 13:37 |  |  |  | 0 |  | When testing the booking location APIs, the {{POST /booking-location-create/}} endpoint failed with a *500 Internal Server Error*, and even after this failure, the {{GET /booking-location-create/}} endpoint returns an *empty list (*{{[]}}*)*, indicating that no booking locations are being stored or fetched. *API Endpoint:* {{http://127.0.0.1:8000/api/booking-location-create/}} # *Requested Body:* * This is a {{GET}} request. h4. Parameters h4. No parameters h4. Curl {noformat}curl -X 'GET' \ 'http://127.0.0.1:8000/api/booking-location-create/' \ -H 'accept: application/json' \ -H 'Authorization: Bearer eyJhbGciOiJIUzI1NiIsInR5cCI6IkpXVCJ9.eyJ0b2tlbl90eXBlIjoiYWNjZXNzIiwiZXhwIjoxNzYyODM0MTUzLCJpYXQiOjE3NjI3NDc3NTMsImp0aSI6Ijc5OGRhYjYzNzNjNzQyNzJiZjM1OGQ0ODJkYjlkNDBmIiwidXNlcl9pZCI6IjEifQ.iTxuQD96mMu1A8kWUl8yei1TdNKhPz3OAzfwlPXqSzI' \ -H 'X-CSRFTOKEN: 79Ds0xmEgFpm7WbLeZ7zPalnKFxony3m'{noformat} h4. Request URL {noformat}http://127.0.0.1:8000/api/booking-location-create/{noformat} h4. h3. *Expected Result:* * The {{POST /booking-location-create/}} should create a booking location successfully (Status *201*). * The {{GET /booking-location-create/}} should list the created booking locations. h3. *Actual Result:* * {{POST}} failed with *KeyError: 'request'* (serializer context missing). * {{GET}} returns *empty array* {{[]}}, indicating no data is stored. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000rj: | Testing |  |  |  |  | 03/Dec/25 11:05 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;RETEST PASSED-DONE |  | In Progress | 2025-12-03 11:05
Testing post booking create location api to create new location API - return error 500 internal server error | SCRUM-130 | 10437 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-10 12:17 | 2025-12-03 13:37 |  |  |  | 0 |  | h4. âœ… API Endpoint: {{POST /booking-location-create/}} h4. âœ… Request Body: {noformat}{ "pickup_id": 1, "dropoff_id": 2 } {noformat} h4. âœ… Headers: {noformat}Authorization: Bearer <your_token> Content-Type: application/json {noformat} h4. âœ… Expected Result: A new booking location should be created successfully. Status Code: *201 Created* Response Body Example: {noformat}{ "id": 3, "pickup_id": 1, "dropoff_id": 2, "message": "Booking location created successfully." } {noformat} h4. âŒ Actual Result: Status Code: *500 Internal Server Error* Error Traceback: {noformat}KeyError at /api/booking-location-create/ 'request' Request Method: POST Request URL: http://127.0.0.1:8000/api/booking-location-create/{noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [10 empty] | SCRUM-141 | SCRUM-143 | [5 empty] | 0¦i000rb: | Testing | 2025-11-10 |  |  |  | 03/Dec/25 10:35 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;RETEST PASSED- DONE |  | In Progress | 2025-11-22 21:41
PUT /trucks/{id}/ API gives â€œTypeError: 'LoadingDetails' object is not iterableâ€ when trying to update truck details. | SCRUM-129 | 10436 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-10 10:53 | 2025-12-03 13:37 |  |  |  | 0 |  | *API Endpoint:* {{http://127.0.0.1:8000/api/trucks/4/}} * *Path Parameter:* {{id = 4}} * *Request Body:* {noformat}{ "name": "Updated Grand Truck Truck", "quantity": 8, "weight_per_unit": 1200, "loading_details": 1, "load_type": 1 }{noformat} *Expected Response:* *Status Code:* 200 OK *Response Body:* {noformat}{ "code": 200, "data": { "id": 4, "name": "Updated Grand Truck", "quantity": 8, "weight_per_unit": 1200, "loading_details": 1, "load_type": 1 }, "message": "Truck updated successfully." }{noformat} h3. *Actual Response* *Status Code:* 500 Internal Server Error *Response Body:* {noformat}TypeError at /api/trucks/4/ 'LoadingDetails' object is not iterable Request Method: PUT Request URL: http://127.0.0.1:8000/api/trucks/4/{noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000r3: | Testing |  |  |  |  | 22/Nov/25 9:49 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest completed. Issue is fixed. |  | In Progress | 2025-11-11 23:49
Testing GET /api/trucks/{id}/ API -- returns 500 Internal Server Error | SCRUM-128 | 10435 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-10 10:34 | 2025-12-03 13:37 |  |  |  | 0 |  | *API Endpoint:* {{GET /api/Truck/{id}/}} *ðŸ”¹ Purpose:* To retrieve details of a specific Truck by its ID. Provides all relevant information *ðŸ”¹ Request Parameters:* ¦¦Name¦¦Description¦¦ ¦idÂ * {noformat}string{noformat} {noformat}{noformat} {noformat}(path){noformat}¦ ¦ *ðŸ”¹ Request Example (cURL):* {noformat}curl -X 'GET' \ 'http://127.0.0.1:8000/api/trucks/2/' \ -H 'accept: application/json' \ -H 'Authorization: Bearer eyJhbGciOiJIUzI1NiIsInR5cCI6IkpXVCJ9.eyJ0b2tlbl90eXBlIjoiYWNjZXNzIiwiZXhwIjoxNzYyODM0MTUzLCJpYXQiOjE3NjI3NDc3NTMsImp0aSI6Ijc5OGRhYjYzNzNjNzQyNzJiZjM1OGQ0ODJkYjlkNDBmIiwidXNlcl9pZCI6IjEifQ.iTxuQD96mMu1A8kWUl8yei1TdNKhPz3OAzfwlPXqSzI' \ -H 'X-CSRFTOKEN: 79Ds0xmEgFpm7WbLeZ7zPalnKFxony3m'{noformat} *ðŸ”¹ Expected Response:* *Status Code:* 201 OK Truck Details *Response Body Example:* {noformat} "code": 201, "data": { "id": 4, "created_at": "2025-11-10T04:49:07.273175Z", "updated_at": "2025-11-10T04:49:07.273229Z", "name": "Grand Truck", "quantity": 5, "weight_per_unit": 1000, "loading_details": 1, "load_type": 1 },{noformat} *ðŸ”¹ Actual Response:* *Status Code:* 500 Internal Server Error *Response Body:* {noformat}AttributeError at /api/trucks/4/ Got AttributeError when attempting to get a value for field `name` on serializer `TruckSerializer`. The serializer field might be named incorrectly and not match any attribute or key on the `Truck` instance. Original exception text was: 'Truck' object has no attribute 'name'.{noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000qv: | Testing |  |  |  |  | 22/Nov/25 9:35 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;DONE | 22/Nov/25 9:48 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest completed. Issue is fixed. | In Progress | 2025-11-11 23:49
GET /trucks/{id}/ API returns 500 Internal Server Error instead of truck details | SCRUM-127 | 10402 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-08 19:30 | 2025-11-20 21:29 |  |  |  | 0 |  | *API Endpoint:* {{http://127.0.0.1:8000/api/trucks/2/}} h3. ðŸ”¹ *Request Body Used* h4. Parameters Cancel ¦¦Name¦¦Description¦¦ ¦idÂ * {noformat}string{noformat} {noformat}{noformat} {noformat}(path){noformat}¦ ¦ *Content-Type:* {{application/json}} *Request URL:* {{http://127.0.0.1:8000/api/trucks/2/}} ¦h3. ðŸ”¹ *Expected Response* *Status Code:* {{200 Truck Details}}¦ h3. ðŸ”¹ *Actual Response* *Status Code:* 500 internal error server *Response Body:* {noformat}AttributeError at /api/trucks/2/ Got AttributeError when attempting to get a value for field `name` on serializer `TruckSerializer`. The serializer field might be named incorrectly and not match any attribute or key on the `Truck` instance. Original exception text was: 'Truck' object has no attribute 'name'. {noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000qn: | [7 empty] | In Progress | 2025-11-20 21:29
Testing GET /trucks/ API - List all trucks API â€” returns 500 Internal Server Error | SCRUM-126 | 10401 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-08 19:16 | 2025-12-03 13:37 |  |  |  | 0 |  | *API Endpoint:* {{GET /trucks/}} *Purpose:* Retrieve a list of all trucks with their details. # *Requested Body:* * This is a {{GET}} request. * *Endpoint:* {{http://127.0.0.1:8000/api/trucks/}} * *Headers:* {noformat}{ "accept": "application/json", "Authorization": "Bearer <valid_access_token>", "X-CSRFTOKEN": "<csrf_token>" } {noformat} * *Parameters:* None *Content-Type:* {{application/json}} *Request URL:* {{http://127.0.0.1:8000/api/trucks/}} h3. ðŸ”¹ *Expected Response* *Status Code:* {{200}} ¦h5. Response body {color:#ffffff}Download{color} {noformat}{ "code": 201, "data": { "id": 2, "created_at": "2025-11-08T11:49:21.054239Z", "updated_at": "2025-11-08T11:49:21.054301Z", "name": "Mini Truck", "quantity": 5, "weight_per_unit": 1000, "loading_details": 1, "load_type": 1 },{noformat}¦ h3. ðŸ”¹ *Actual Response* *Status Code:* 500 Internal Server Error *Response Body:* {noformat}AttributeError at /api/trucks/ Got AttributeError when attempting to get a value for field `name` on serializer `TruckSerializer`. The serializer field might be named incorrectly and not match any attribute or key on the `Truck` instance. Original exception text was: 'Truck' object has no attribute 'name'. {noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000qf: | Testing |  |  |  |  | 22/Nov/25 9:34 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;DONE | 22/Nov/25 9:48 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest completed. Issue is fixed. | In Progress | 2025-11-11 23:48
PUT /api/items/{id}/ fails with 404 when updating existing item | SCRUM-125 | 10400 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-08 17:04 | 2025-12-03 13:37 |  |  |  | 0 |  | *API Endpoint:* {{http://127.0.0.1:8000/api/api/items/2/}} *API Endpoint:* [http://127.0.0.1:8000/api/api/items/2/¦http://127.0.0.1:8000/api/api/items/2/] *Purpose / Issue:* When updating an existing truck item using PUT {{/api/items/{id}/}}, the API returns 404 "No Item matches the given query." even though the item exists. *Steps to Reproduce:* # Create a truck item using POST /api/createitems/: { "truck_number": "RJ14AB1234", "truck_type": "Mini Truck", "capacity_in_tons": 5, "current_location": "Jaipur", "driver_name": "Ramesh Kumar", "driver_contact": "9876543210", "driver_license_number": "RJDL123456789", "is_available": true, "last_known_lat": "26.9124", "last_known_lng": "75.7873" } # Take note of the {{id}} returned (e.g., 2). # Attempt to update the item with PUT /api/items/2/: { "truck_number": "RJ14AB1234", "truck_type": "Mini Truck", "capacity_in_tons": 6, "current_location": "Jaipur", "driver_name": "Ramesh Kumar", "driver_contact": "9876543210", "driver_license_number": "RJDL123456789", "is_available": false, "last_known_lat": "26.9124", "last_known_lng": "75.7873" } *Actual Result:* * API returns 404 error: { "detail": "No Item matches the given query." } *Expected Result:* * API should return 200 OK with updated truck item details. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000q7: | Testing |  |  |  |  | 22/Nov/25 9:48 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest completed. Issue is fixed. |  | In Progress | 2025-11-11 23:44
GET /api/items/{id}/ returns 500 Internal Server Error | SCRUM-124 | 10399 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-08 14:12 | 2025-12-03 13:36 |  |  |  | 0 |  | *API Endpoint:* {{GET /api/items/{id}/}} *ðŸ”¹ Purpose:* To retrieve details of a specific item by its ID. Provides all relevant information such as truck number, type, capacity, driver details, and location. *ðŸ”¹ Request Parameters:* ¦¦Name¦¦Type¦¦Required¦¦Description¦¦Example¦¦ ¦id¦string¦_Yes_¦The unique ID of the item to retrieve¦1¦ *ðŸ”¹ Request Example (cURL):* {noformat}curl -X 'GET' \ 'http://127.0.0.1:8000/api/api/items/1/' \ -H 'accept: application/json' \ -H 'Authorization: Bearer <access_token>' \ -H 'X-CSRFTOKEN: <csrftoken>' {noformat} *ðŸ”¹ Expected Response:* *Status Code:* 200 OK *Response Body Example:* {noformat}{ "id": 1, "truck_number": "TN01AB1234", "truck_type": "Truck", "capacity_in_tons": 10, "current_location": "Jaipur", "driver_name": "John Doe", "driver_contact": "9876543210", "driver_license_number": "DL123456", "is_available": true, "last_known_lat": "26.9124", "last_known_lng": "75.7873", "created_at": "2025-11-08T08:00:00Z", "updated_at": "2025-11-08T08:30:00Z" } {noformat} *ðŸ”¹ Actual Response:* *Status Code:* 500 Internal Server Error *Response Body:* {noformat}AttributeError at /api/api/items/1/ Got AttributeError when attempting to get a value for field `truck_number` on serializer `ItemSerializer`. The serializer field might be named incorrectly and not match any attribute or key on the `Item` instance. Original exception text was: 'Item' object has no attribute 'truck_number'.{noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000pz: | Testing |  |  |  |  | 22/Nov/25 9:48 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest completed. Issue is fixed. | 03/Dec/25 10:25 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest Passed â€” Done | In Progress | 2025-11-11 23:44
GET /api/createitems/ endpoint returns 500 Internal Server Error | SCRUM-123 | 10398 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-08 14:03 | 2025-12-03 13:36 |  |  |  | 0 |  | *API Endpoint:* {{GET /api/api/createitems/}} *ðŸ”¹ Purpose:* To fetch a list of all items. h3. *ðŸ”¹ Request Parameters:* ¦¦Name¦¦Location¦¦Type¦¦Description¦¦ ¦load_type¦query¦string¦Optional. Filter items by associated load type name.¦ *Content-Type:* {{application/json}} *Request URL:* {{http://127.0.0.1:8000/api/api/createitems/}} h3. ðŸ”¹ *Expected Response* ¦Code¦Description¦ ¦200¦List of items.¦ *ðŸ”¹ Actual Response:* * *Status Code:* 500 Internal Server Error * *Response Body:* {noformat}{ "detail": "Got AttributeError when attempting to get a value for field `truck_number` on serializer `ItemSerializer`. The serializer field might be named incorrectly and not match any attribute or key on the `Item` instance. Original exception text: 'Item' object has no attribute 'truck_number'." }{noformat} {noformat}AttributeError at /api/api/createitems/ Got AttributeError when attempting to get a value for field `truck_number` on serializer `ItemSerializer`. The serializer field might be named incorrectly and not match any attribute or key on the `Item` instance. Original exception text was: 'Item' object has no attribute 'truck_number'.{noformat} |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000pr: | Testing |  |  |  |  | 22/Nov/25 9:48 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest completed. Issue is fixed. | 03/Dec/25 10:25 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest Passed â€” Done | In Progress | 2025-11-11 23:43
Testing â€œSend Login Phone OTPâ€ API â€” returns 400 Bad Request (User with this phone number does not exist) | SCRUM-122 | 10365 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-07 16:44 | 2025-12-03 13:36 |  |  |  | 0 |  | *API Endpoint:* POST {{/api/send-login-phone-otp/}} *Purpose:* Send OTP to the provided phone number for login authentication. *Request Body:* {noformat}{ "phone": "7014738641" } {noformat} *Content-Type:* {{application/json}} *Expected Response:* Status Code 200 OK, OTP sent successfully. *Actual Response:* Status Code 400 Bad Request {noformat}{ "code": 400, "error": { "non_field_errors": [ "User with this phone number does not exist." ] } } {noformat} *Issue Description:* The API returns a 400 error when the phone number provided does not exist in the system. Proper validation is working, but the request fails due to invalid input. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000pj: | Testing |  |  |  |  | 22/Nov/25 9:31 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;DONE | 22/Nov/25 9:47 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest completed. Issue is fixed. | In Progress | 2025-11-11 20:46
Testing â€œSend Login Phone OTPâ€ API â€” returns 500 Internal Server Error | SCRUM-121 | 10364 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-07 16:42 | 2025-12-03 13:36 |  |  |  | 0 |  | *API Endpoint:* {{POST /api/send-login-email-otp/}} *ðŸ”¹ Purpose:* Send OTP to the provided email for login authentication. *ðŸ”¹ Request Body Used:* {noformat}{ "email": "varshabansal25032503@gmail.com" } {noformat} *Content-Type:* {{application/json}} *Request URL:* {{http://127.0.0.1:8000/api/send-login-email-otp/}} *ðŸ”¹ Expected Response:* *Status Code:* 200 OK *Expected Output:* {noformat}{ "success": true, "message": "OTP sent successfully.", "data": {} } {noformat} *ðŸ”¹ Actual Response:* *Status Code:* 500 Internal Server Error *Response Body:* {noformat}TypeError at /api/send-login-email-otp/ unsupported operand type(s) for /: 'float' and 'str' {noformat} *ðŸ”¹ Issue Description:* The API throws a TypeError in the backend: {{unsupported operand type(s) for /: 'float' and 'str'}}. This occurs during OTP generation, indicating a bug in the {{totp.timecode()}} calculation. Despite valid input, the OTP cannot be generated and the API fails with a 500 error instead of sending the OTP. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000pb: | Testing |  |  |  |  | 22/Nov/25 9:47 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest completed. Issue is fixed. | 03/Dec/25 10:25 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest Passed â€” Done | In Progress | 2025-11-11 20:47
Send Login Email OTP API | SCRUM-120 | 10363 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-07 16:35 | 2025-12-03 13:36 |  |  |  | 0 |  | *API Endpoint:* {{POST /api/send-login-email-otp/}} *ðŸ”¹ Purpose:* Send OTP to the provided email for login authentication. *ðŸ”¹ Request Body Used:* {noformat}{ "email": "varshabansal25032503@gmail.com" } {noformat} *Content-Type:* {{application/json}} *Request URL:* {{http://127.0.0.1:8000/api/send-login-email-otp/}} *ðŸ”¹ Expected Response:* *Status Code:* 200 OK *Expected Output:* {noformat}{ "success": true, "message": "OTP sent successfully.", "data": {} } {noformat} *ðŸ”¹ Actual Response:* *Status Code:* 500 Internal Server Error *Response Body:* {noformat}TypeError at /api/send-login-email-otp/ unsupported operand type(s) for /: 'float' and 'str' {noformat} *ðŸ”¹ Issue Description:* The API throws a {{TypeError}} in the backend: {{unsupported operand type(s) for /: 'float' and 'str'}} This occurs during OTP generation, indicating a bug in the {{totp.timecode()}} calculation. Despite valid input, the OTP cannot be generated and the API fails with a 500 error instead of sending the OTP. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000p3: | Testing |  |  |  |  | 22/Nov/25 9:47 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest completed. Issue is fixed. | 03/Dec/25 10:24 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest Passed â€” Done | In Progress | 2025-11-11 20:38
Testing â€œRegister With Referralâ€ API â€” returns 400 Bad Request (username required) | SCRUM-119 | 10330 | Story | Testing | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-07 12:15 | 2025-12-03 13:37 | 2025-12-22 19:30 |  |  | 0 |  | *API Endpoint:* {{POST /api/register-with-referral/}} *ðŸ”¹ Purpose:* To register a new user using a referral code. Applies bonus to both referrer and new user. ---- h3. ðŸ”¹ *Request Body Used* {noformat}{ "phone": "7014738622", "password": "Varsha@2502", "referral_code": "172cec62" } {noformat} *Content-Type:* {{application/json}} *Request URL:* {{http://127.0.0.1:8000/api/register-with-referral/}} ---- h3. ðŸ”¹ *Expected Response* *Status Code:* {{201 Created}} *Expected Output:* {noformat}{ "message": "User registered successfully." } {noformat} ---- h3. ðŸ”¹ *Actual Response* *Status Code:* {{400 Bad Request}} *Response Body:* {noformat}{ "username": [ "This field is required." ] } {noformat} ðŸ”¹ *Issue Description* Even though the API model shows {{phone}} as an acceptable input, the backend is returning {{"username": ["This field is required."]}}, indicating a mismatch between API documentation and backend validation logic. |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [10 empty] | SCRUM-138 |  |  | SCRUM-117 |  |  |  | 0¦i000tn: | Testing |  | 1 |  |  | 22/Nov/25 9:29 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest Issue Observed: * API endpoint: POST /api/register-with-referral/ * Test data: { "username": "sitaram_23", "password": "Varsha@2503", "referral_code": "172cec62" } * Response: 400 Invalid referral code (even though referral code is valid) * Side effect: Despite 400 response, user "sitaram_23" is created in DB Steps Performed: # Sent POST request with valid referral code. # Observed 400 response. # Verified DB â†’ user created. Re-test Result: FAILED |  | In Progress | 2025-11-10 22:13
Test register-with-referral API endpoint | SCRUM-118 | 10297 | Story | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-06 17:29 | 2025-12-03 13:36 |  |  |  | 0 |  | Allow new users to register on the platform using email/phone and an optional referral code. The backend should handle user creation, validate referral codes, and apply referral bonuses to both the referrer and the new user. â€œQA intern reporting this bug â€“ please assign to the relevant developer.â€ |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | [17 empty] | 0¦i000on: | Testing | 2025-11-06 |  |  |  | 03/Dec/25 10:24 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest Passed â€” Done |  | In Progress | 2025-11-22 08:36
Registration API fails with "m user required" | SCRUM-117 | 10264 | Task | In Dev Branch | SCRUM | Byto Backend | software | Krishnakant Singhal | 712020:acff4cd7-6975-438e-947b-71ce4c05dddd | Your first project | Medium |  | Rohith Gangarapu | 712020:add1ea9b-f4e2-49ed-8c9f-c7d720b69a1b | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | varsha bansal | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 | 2025-11-05 17:20 | 2025-12-03 13:36 |  |  |  | 0 | qa | As a QA intern, I tested the Registration API and found a bug. Steps to reproduce: # Send POST request to /register-with-referral/ with valid email, password, phone, and country. # API returns "m user required" error. Expected: User should be registered successfully. Observed: API gives an error and does not register the user. â€œThis is a test task for learning purposesâ€ |  | varsha bansal |  | 712020:e56a999e-31c2-4566-af9d-0ba62f0ff271 |  | me log;06/Nov/25 9:54 AM;ug:2b6d8e79-b599-44ee-8758-8321bcb94959;120 |  | 0 | 120 |  |  | 0 | 120 |  | SCRUM-119 | [6 empty] | 0¦i000of: | Testing |  |  |  |  | 03/Dec/25 10:23 AM;712020:e56a999e-31c2-4566-af9d-0ba62f0ff271;Retest Passed â€” Done |  | In Progress | 2025-11-10 22:10